## Sheet1
Division | Initiative | Strategic Objective | ITD Objectives | Divisional KPI | ITD KPI | ITD KPI Score | Start Date | End Date | Activities | January Activities | Jan Weighing Average (%) | Jan Score | February Activities | Feb Weighing Average | Feb Score | March Activities | March Weighing Average | Mar Score | April Activities | April Weighing Average | April Score | May Activities | May Weighing Average | May Score | June Activities | June Weighing Average | June Score | July Activities | July Weighing Average | July Score | August Activities | August Weighing Average | August Score | September Activities | September weighing Average | September Score | October Activities | October weighing average | October Score | November Activities | November weighing average | November Score | December Activities | December weighing average | December Score | Is Target Met? | Is Initiative Active? | Year | Total Weight | Total Score
AMD | Liquidity Forecasting Phase II (2026) | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery |  | ["100% technology projects that achieve at least 80% of intended benefits"] |  | 2026-01-04 | 12/31/2026 | Model development | Awaiting work plan from BRM | 0% |  | Phase II workplan development. Requirements gathering | 0% | 0% | Net FGN operations models develoment | 5% | 5% | Domestic operations models develoment | 15% | 0% | Foreign operations models develoment | 15% | 10% | FAAC models develoment | 13% | 13% | Change in CIC models develoment | 13% | 0% | System test | 13% | 0% | UAT & Go live | 13% | 0% | Post go live support | 5% | 0% |  | 0% | 0% |  | 25% | 0% |  | TRUE | 2026 | Sum of Jan - Dec Weighing Average must be equal 100% | 28%
Model evaluation and review
Data visualisation and interpretation
User training
User acceptance test
Go live
AMD | BI One | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery |  | ["None"] |  | 2026-01-04 | 11/30/2026 | Develop document store module |  | 0% |  |  | 0% | 0% |  | 0% | 0% | Develop document upload feature. | 15% | 0% | Implement template management | 15% | 0% | Set up data upload verification process. | 10% | 0% | Integrate notification system for approvals. | 10% | 0% | Unit, System and User Acceptance Tests | 5% | 0% | Commencement of Phase 3; | 15% | 0% | Implement AI Chat feature to interact with datasets using natural language. | 15% | 0% | Unit, System and User Acceptance Tests | 5% | 0% | Deploy the application to a staging environment for final testing. | 10% | 0% |  | TRUE | 2026 | 100% | 0%
[9 empty] | Perform tests (unit, system and user acceptance) | [24 empty] | Implement dataset browsing functionality.
[9 empty] | Bug fixes and optimization | [21 empty] | Bug Fixing and Optimization | [8 empty] | Bug Fixing and Optimization |  |  | Deploy the application to production environment.
Enable data table view with filtering
Add Export options for CSV and Excel
AMD | DataOps Modernization - Optimize Data Assets for GenAI and Digital Transformation | ECBO 1 - Enhance efficiency in service delivery, supervisory oversight and transparency with accelerated shift to a technology-powered and digital operated Central Bank. | Automate identified core processes in the Bank to enable digital transformation |  | ["20% increase in core processes of the Bank that are technology enabled"] |  | 2026-01-02 | 9/30/2026 | i. Project Kick-off and planning - | Project Kick-off and planning | 5% |  | Assess Current State | 10% |  | Design DataOps Architecture | 10% |  | Implement Automation: Automate data ingestion abnd transformation, testing and continuous integration. | 10% |  | Implement Automation: Automate data ingestion abnd transformation, testing and continuous integration (cont'd) | 10% |  | Implement Automation: Automate data ingestion abnd transformation, testing and continuous integration (cont'd) | 10% |  | Implement Data Quality and Security | 10% |  | Implement Data Quality and Security | 10% |  | Conduct System Test and UAT. | 15% | [5 empty] | 0% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 98%
ii. Define Objectives Governance
[9 empty] | iii. Assess Current State | Define Objectives Governance | [23 empty] | Deploy to production
iv. Design DataOps Architecture
[9 empty] | v. Implement Automation: Automate data ingestion abnd transformation, testing and continuous integration. | [24 empty] | Continuous Monitoring and Improvement.
vi. Implement Data Quality and Security
vii. Conduct System Test and UAT.
viii. Deploy to production
ix. Continuous Monitoring and Improvement.
AMD | MLOps Framework Implementation | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery |  | ["20% increase in core processes of the Bank that are technology enabled"] |  | 2026-02-03 | 12/31/2026 | Project Initiation and Planning |  | 0% |  |  | 0% |  | Define project scope, objectives, and success metrics. | 10% |  | Set up data versioning tools . | 10% |  | Implement experiment tracking | 10% |  | CI/CD Pipeline for ML | 15% |  | Set up container orchestration . | 10% |  | Set up container orchestration . | 10% |  | Monitoring and Logging: Implement model performance monitoring (drift detection) | 10% |  | Monitoring and Logging: Implement model performance monitoring (drift detection) | 10% |  | Implement audit trails for data and models. | 10% |  | Conduct System Test and UAT. | 5% |  |  | FALSE | 2026 | 100% | 0%
[9 empty] | Develop solution architecture and workflow | [9 empty] | Configure development environments |  |  | Define model packaging standards | [5 empty] | Deploy initial models to staging environment. |  |  | Deploy initial models to staging environment. |  |  | Set up logging and alerting systems. |  |  | Set up logging and alerting systems.
[9 empty] | Environment setup and model development framework | [6 empty] | Identify stakeholders and form MLOps Team | [11 empty] | Implement API endpoints for model serving. |  |  | Implement API endpoints for model serving. | [11 empty] | Deploy to production
Continuous integration and delivery Pipeline
[9 empty] | Logging and tracking for drift detection | [33 empty] | Continuous Monitoring and Improvement.
System Test and UAT
Deployment
AMD | Finance Companies Module (OFIS) (New Regulatory Application) | RRFS 3 - Leverage technology and innovation to ensure a secured, efficient, transparent, reliable and scalable payment and financial system that positions Nigeria as a key financial centre. | None | 40% of identified payment and regulatory processes delivered | ["None"] |  | 2026-01-01 | 2026-03-31 | Team Nomination | Integration testing, Conference room pilot/demo sessions | 10% |  | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | [28 empty] | TRUE | 2026 | =100% OK | 0%
Stakeholders Engagement
[9 empty] | Requirement Review | [6 empty] | Go-live
Solution Architecture Review
Functional Training/workshop
Solution Design
Server Provisioning
Solution Design
Technical Training
Solution Development
Unit Testing
Solution Review
Documentation
Training
System Test
UAT
Implementation
Onboarding of FIs
Go Live
AMD | Reg Data Core Module (PaSSD) (New Regulatory Application) | RRFS 3 - Leverage technology and innovation to ensure a secured, efficient, transparent, reliable and scalable payment and financial system that positions Nigeria as a key financial centre. | None | 40% of identified payment and regulatory processes delivered | ["None"] |  | 2026-01-01 | 2026-03-31 | Team Nomination | Integration testing, Conference room pilot/demo sessions | 10% |  | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | [28 empty] | TRUE | 2026 | =100% OK | 0%
Stakeholders Engagement
[9 empty] | Requirement Review | [6 empty] | Go-live
Solution Architecture Review
Functional Training/workshop
Solution Design
Server Provisioning
Solution Design
Technical Training
Solution Development
Unit Testing
Solution Review
Documentation
Training
System Test
UAT
Implementation
Onboarding of FIs
Go Live
AMD | Prudential Reporting for BDCs Module (DFISD) (New Regulatory Application) | RRFS 3 - Leverage technology and innovation to ensure a secured, efficient, transparent, reliable and scalable payment and financial system that positions Nigeria as a key financial centre. | None | 40% of identified payment and regulatory processes delivered | ["None"] |  | 2026-01-01 | 2026-03-31 | Team Nomination | Integration testing, Conference room pilot/demo sessions | 10% |  | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | [28 empty] | TRUE | 2026 | =100% OK | 0%
Stakeholders Engagement
[9 empty] | Requirement Review | [6 empty] | Go-live
Solution Architecture Review
Functional Training/workshop
Solution Design
Server Provisioning
Solution Design
Technical Training
Solution Development
Unit Testing
Solution Review
Documentation
Training
System Test
UAT
Implementation
Onboarding of FIs
Go Live
AMD | FIFX Module Rebuild (TED) (New Regulatory Application) | RRFS 3 - Leverage technology and innovation to ensure a secured, efficient, transparent, reliable and scalable payment and financial system that positions Nigeria as a key financial centre. | None | 40% of identified payment and regulatory processes delivered | ["None"] |  | 2026-01-01 | 2026-03-31 | Team Nomination | Integration testing, Conference room pilot/demo sessions | 10% |  | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | [28 empty] | TRUE | 2026 | =100% OK | 0%
Stakeholders Engagement
[9 empty] | Requirement Review | [6 empty] | Go-live
Solution Architecture Review
Functional Training/workshop
Solution Design
Server Provisioning
Solution Design
Technical Training
Solution Development
Unit Testing
Solution Review
Documentation
Training
System Test
UAT
Implementation
Onboarding of FIs
Go Live
AMD | RegFlow Module (PaSSD) (LARP) | RRFS 3 - Leverage technology and innovation to ensure a secured, efficient, transparent, reliable and scalable payment and financial system that positions Nigeria as a key financial centre. | None | 40% of identified payment and regulatory processes delivered | ["None"] |  | 2026-01-01 | 2026-03-31 | Team Nomination | Integration testing, Conference room pilot/demo sessions | 10% |  | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | [28 empty] | TRUE | 2026 | =100% OK | 0%
Stakeholders Engagement
[9 empty] | Requirement Review | [6 empty] | Go-live
Solution Architecture Review
Functional Training/workshop
Solution Design
Server Provisioning
Solution Design
Technical Training
Solution Development
Unit Testing
Solution Review
Documentation
Training
System Test
UAT
Implementation
Onboarding of FIs
Go Live
AMD | NCR Portal Enhancement | ECBO 1 - Enhance efficiency in service delivery, supervisory oversight and transparency with accelerated shift to a technology-powered and digital operated Central Bank. | Enhance efficiency in service delivery to a technology-powered and digital operated Central Bank. | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% increase in core processes of the Bank that are technology enabled"] |  | 2026-01-01 | 2026-10-31 | General Enhancements on the National Collateral Registry to automate processes, improve performance and user experience. | 1.Stakeholder engagemnt sessions and workshops | 10% |  | 1.Requiremnts gathering and analysis | 10% | 0% | 1. Document Change Request and Obtain CAB Approval | 10% | 0% | System design and documentation, Technical specifications | 10% | 0% | Front end development and unit testing | 10% | 0% | Back end development and unit testing. | 10% | 0% | External services adpter development and unit testing | 10% | 0% | Integration testing, Conference room pilot/demo sessions | 10% | 0% | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | G | 0% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 0%
1. Document Requirements
[9 empty] | 2. Obtain CAB approval | [12 empty] | API service development and unit testing |  |  | Database artifacts development and unit testing | [11 empty] | Go-live
3. Design and Develop
4. Test solutio
5. Implement and Go-Live.
AMD | Integration of eCCI/CSCS | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | 40% of identified payment and regulatory processes delivered | ["20% Efficiency of Central Banking Process"] |  | 2025-03-02 | 2025-07-31 | Requiremnts documentation and analysis, sign-off of requirements, API client development, Development of eCCI-CSCS connector, unit testing, integration testing, system test and UAT | 1.Stakeholder engagemnt sessions and workshops | 10% |  | 1.Requiremnts revalidation and analysis | 10% | 0% | 1. Document Change Request and Obtain CAB Approval | 10% | 0% | System design and documentation, Technical specifications | 10% | 0% | Front end development and unit testing | 10% | 0% | Back end development and unit testing. | 10% | 0% | External services adpter development and unit testing | 10% | 0% | Integration testing, Conference room pilot/demo sessions | 10% | 0% | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | G | 0% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 0%
[22 empty] | API service development and unit testing |  |  | Database artifacts development and unit testing | [11 empty] | Go-live
AMD | Redesigned Credit Risk Management System (2025) | ECBO 1 - Enhance efficiency in service delivery, supervisory oversight and transparency with accelerated shift to a technology-powered and digital operated Central Bank. | Enhance efficiency in service delivery to a technology-powered and digital operated Central Bank. | 40% of identified payment and regulatory processes delivered | ["100% technology projects that achieve at least 80% of intended benefits"] |  | 2026-01-01 | 2026-02-28 | CRMS UAT | 1.GSI UAT | 50% |  | 1.GSI UAT-GO LIVE | 50% | 0% | [31 empty] | TRUE | 2026 | =100% OK | 0%
GSI Testing with NIBSS and Banks
Decision on Deployment Approach
Code and Vulnerability Scans
Server Provisioning
Deployment on Servers
User Creation
Go live
Onboarding of Fis
AMD | Licensing, Approvals & Other Reports Portal Licensing of Mobile Money Operators | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-01-01 | 2026-10-31 | Obtain CAB Approval for BDC Module | 1.Stakeholder engagemnt sessions and workshops | 10% |  | 1.Requiremnts gathering and analysis | 10% | 0% | 1. Document Change Request and Obtain CAB Approval | 10% | 0% | System design and documentation, Technical specifications | 10% | 0% | Front end development and unit testing | 10% | 0% | Back end development and unit testing. | 10% | 0% | External services adpter development and unit testing | 10% | 0% | Integration testing, Conference room pilot/demo sessions | 10% | 0% | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | G | 0% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 0%
Review BDC module with FPRD
[9 empty] | Update BDC Module based on Review Conducted | [12 empty] | API service development and unit testing |  |  | Database artifacts development and unit testing | [11 empty] | Go-live
Conduct System Test and UAT on BDC Module
Conduct System Test and UAT on Cheque Printer
Conduct Training to users on BDC Module
Conduct Training to users on Cheque Printer Module
Implementation of Cheque Printer &amp; BDC Module
AMD | Licensing, Approvals & Other Reports Portal Licensing of PSSPs | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-01-01 | 2026-10-31 | Obtain CAB Approval for BDC Module | 1.Stakeholder engagemnt sessions and workshops | 10% |  | 1.Requiremnts gathering and analysis | 10% | 0% | 1. Document Change Request and Obtain CAB Approval | 10% | 0% | System design and documentation, Technical specifications | 10% | 0% | Front end development and unit testing | 10% | 0% | Back end development and unit testing. | 10% | 0% | External services adpter development and unit testing | 10% | 0% | Integration testing, Conference room pilot/demo sessions | 10% | 0% | Manual develoment and user training | 10% | 0% | System tests/UAT | 10% | 0% | G | 0% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 0%
Review BDC module with FPRD
[9 empty] | Update BDC Module based on Review Conducted | [12 empty] | API service development and unit testing |  |  | Database artifacts development and unit testing | [11 empty] | Go-live
Conduct System Test and UAT on BDC Module
Conduct System Test and UAT on Cheque Printer
Conduct Training to users on BDC Module
Conduct Training to users on Cheque Printer Module
Implementation of Cheque Printer &amp; BDC Module
AMD | Sabimoni Upgrade | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity
AMD | Performance Management System | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2025-10-02 | 5/31/2025 | 1. Solution Developement to Fix Pilot Run issues | 1. Solution Developement | 20% |  | 1. Unit testing | 20% | 20% | 5. Users Training | 30% | 30% | 1. Deployement to Production | 20% | 20% | 1. Go Live | 10% | 10% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | TRUE | 2025 | =100% OK | 100%
[9 empty] | 2. Integration of Componets and Interfaces on Pilot run Issues | 2. Integration of Components and Interfaces |  |  | 2. System Test |  |  | 6. Users Accaeptance Test (UAT) |  |  | 2. Pilot Run
3. Unit Testing
4. System Test
5. Users Accaeptance Test (UAT)
6. Deployement to Production
7. Go Live
AMD | Budget Automation System | ECBO 1 - Enhance efficiency in service delivery, supervisory oversight and transparency with accelerated shift to a technology-powered and digital operated Central Bank. | Automate identified core processes in the Bank to enable digital transformation | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% increase in core processes of the Bank that are technology enabled"] |  | 2025-03-03 | 8/31/2025 | 1. Secure Management Approval | 1. Secure Management Approval | 10% |  | 1. Document requirement | 10% | 10% | 1. Solution Design | 20% | 20% | 1. Solution Developement | 10% | 10% | 1. Development and Integration of Componets and Interfaces. | 10% | 10% | 1. Progress Demonstartion to Stakeholders. | 10% | 10% | 1. System Test. | 20% | 20% | 1. Users and System support Training. | 10% | 10% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | TRUE | 2025 | =100% OK | 100%
[9 empty] | 2. Document requirement |  |  |  | 2. Solution Architecture | [11 empty] | 2. Unit Testing |  |  | 2. Documetation of Technical and Users Mannual. |  |  | 2. Users Accaeptance Test (UAT)
[9 empty] | 3. Solution Architecture | [21 empty] | 3. Deployement to Production
[9 empty] | 4. Solution Design | [21 empty] | 14. Go Live
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | Procurement Management System | ECBO 1 - Enhance efficiency in service delivery, supervisory oversight and transparency with accelerated shift to a technology-powered and digital operated Central Bank. | Enhance efficiency in service delivery to a technology-powered and digital operated Central Bank. | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% increase in core processes of the Bank that are technology enabled"] |  | 2025-03-03 | 9/30/2025 | 1. Secure Management Approval | 1. Secure Management Approval | 10% |  | 1. Document requirement | 10% | 10% | 1. Solution Design | 15% | 15% | 1. Solution Developement | 10% | 10% | 1. Development and Integration of Componets and Interfaces. | 10% | 10% | 1. Progress Demonstartion to Stakeholders. | 10% | 5% | 1. System Test. | 20% | 0% | 12. External Stakeholders sensitiazation | 5% | 0% | 1. Users and System support Training. | 10% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | TRUE | 2025 | =100% OK | 60%
[9 empty] | 2. Document requirement |  |  |  | 2. Solution Architecture | [11 empty] | 2. Unit Testing |  |  | 2. Documetation of Technical and Users Mannual. | [5 empty] | 2. Users Accaeptance Test (UAT)
[9 empty] | 3. Solution Architecture | [24 empty] | 3. Deployement to Production
[9 empty] | 4. Solution Design | [24 empty] | 14. Go Live
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. External Stakeholders sensitiazation
13. Users Accaeptance Test (UAT)
14. Deployement to Production
15. Go Live
AMD | DocFlow - EasyPay | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2025-10-02 | 5/31/2025 | 1. Requirement Ellicitation | 1.Requirement Ellicitation | 20% |  | 1. Solution Developement | 0% | 0% | 1. Unit Testing | 0% | 0% | 1. Users Accaeptance Test (UAT) | 0% | 0% | 1. Pilot Run | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 40% | 0% |  | 40% | 0% |  | 0% | 0% |  | TRUE | 2025 | =100% OK | 20%
[9 empty] | 2. Solution Developement |  |  |  | 2. Integration of Componets and Interfaces to ERP |  |  | 2. System Test |  |  | 2. Deployement to Production |  |  | 2. Go Live
[9 empty] | 3. Integration of Componets and Interfaces to ERP | [6 empty] | 3. Users Training
3. Unit Testing
4. System Test
5. Users Training
6. Users Accaeptance Test (UAT)
7. Deployement to Production
8. Pilot Run
9. Go Live
AMD | DocFlow Optimisation | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-05-02 | 5/31/2026 | 1. Requirement Ellicitation | 1.Requirement Ellicitation | 20% |  | 1. Solution Developement | 0% | 0% | 1. Unit Testing | 0% | 0% | 1. Users Acceptance Test (UAT) | 0% | 0% | 1. Pilot Run | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 40% | 0% |  | 40% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 20%
[9 empty] | 2. Solution Developement |  |  |  | 2. Integration of Componets and Interfaces to ERP |  |  | 2. System Test |  |  | 2. Deployment to Production |  |  | 2. Go Live
[9 empty] | 3. Integration of Componets and Interfaces to ERP | [6 empty] | 3. Users Training
3. Unit Testing
4. System Test
5. Users Training
6. Users Accaeptance Test (UAT)
7. Deployement to Production
8. Pilot Run
9. Go Live
AMD | Custom Process Automation Enhancement | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-05-02 | 6/30/2026 | 1. Requirement Ellicitation | 1.Requirement Ellicitation | 20% |  | 1. Solution Developement | 0% | 0% | 1. Unit Testing | 0% | 0% | 1. Users Acceptance Test (UAT) | 0% | 0% | 1. Pilot Run | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 40% | 0% |  | 40% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 20%
[9 empty] | 2. Solution Developement |  |  |  | 2. Integration of Componets and Interfaces to ERP |  |  | 2. System Test |  |  | 2. Deployment to Production |  |  | 2. Go Live
[9 empty] | 3. Integration of Componets and Interfaces to ERP | [6 empty] | 3. Users Training
3. Unit Testing
4. System Test
5. Users Training
6. Users Accaeptance Test (UAT)
7. Deployement to Production
8. Pilot Run
9. Go Live
AMD | MDA Payment Enhancements | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-05-02 | 5/31/2026 | 1. Requirement Ellicitation | 1.Requirement Ellicitation | 20% |  | 1. Solution Developement | 0% | 0% | 1. Unit Testing | 0% | 0% | 1. Users Acceptance Test (UAT) | 0% | 0% | 1. Pilot Run | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 40% | 0% |  | 40% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 20%
[9 empty] | 2. Solution Developement |  |  |  | 2. Integration of Componets and Interfaces to ERP |  |  | 2. System Test |  |  | 2. DeploymenteployemDent to Production |  |  | 2. Go Live
[9 empty] | 3. Integration of Componets and Interfaces to ERP | [6 empty] | 3. Users Training
3. Unit Testing
4. System Test
5. Users Training
6. Users Accaeptance Test (UAT)
7. Deployement to Production
8. Pilot Run
9. Go Live
AMD | SMARTGATE Enhancements | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-05-02 | 6/30/2026 | 1. Requirement Ellicitation | 1.Requirement Ellicitation | 20% |  | 1. Solution Developement | 0% | 0% | 1. Unit Testing | 0% | 0% | 1. Users Acceptance Test (UAT) | 0% | 0% | 1. Pilot Run | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 40% | 0% |  | 40% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 20%
[9 empty] | 2. Solution Developement |  |  |  | 2. Integration of Componets and Interfaces to ERP |  |  | 2. System Test |  |  | 2. Deployment to Production |  |  | 2. Go Live
[9 empty] | 3. Integration of Componets and Interfaces to ERP | [6 empty] | 3. Users Training
3. Unit Testing
4. System Test
5. Users Training
6. Users Accaeptance Test (UAT)
7. Deployement to Production
8. Pilot Run
9. Go Live
AMD | Mint Tracking/i-Tracker Upgrade | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-05-02 | 9/30/2026 | 1. Requirement Ellicitation | 1.Requirement Ellicitation | 20% |  | 1. Solution Developement | 0% | 0% | 1. Unit Testing | 0% | 0% | 1. Users Accaptance Test (UAT) | 0% | 0% | 1. Pilot Run | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | 40% | 0% |  | 40% | 0% |  | 0% | 0% |  | TRUE | 2026 | =100% OK | 20%
[9 empty] | 2. Solution Developement |  |  |  | 2. Integration of Componets and Interfaces to ERP |  |  | 2. System Test |  |  | 2. Deployment to Production |  |  | 2. Go Live
[9 empty] | 3. Integration of Componets and Interfaces to ERP | [6 empty] | 3. Users Training
3. Unit Testing
4. System Test
5. Users Training
6. Users Accaeptance Test (UAT)
7. Deployement to Production
8. Pilot Run
9. Go Live
AMD | Bloomberg AIM Project (Phase 2) and onboarding Financial Market Dept on AIM (2025) | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-01-01 | 6/30/2026 | User Training for FMD Staff | 1. User Training for FMD Staff | 10% |  | 1. User Training for FMD Staff | 10% | 10% | 1. User Training for FMD Staff | 15% | 15% | 1. Bloomberg AIM Integration for IRS (BETA) | 20% | 10% | 1. System Test | 15% | 15% | 1. Data Migration from WSS to Bloomberg AIM Prod Environment | 10% | 5% | 1. UAT | 5% | 0% |  | 5% | 0% |  | 5% | 0% | 1. Post Go-Live Support | 5% | 0% |  | 0% | 0% |  | 0% | 0% |  | TRUE | 2025 | =100% OK | 65%
[9 empty] | Bloomberg AIM Integration for IRS (BETA) | [6 empty] | 2. Bloomberg AIM Integration for IRS (BETA) | [5 empty] | 2. UAT |  |  | 2. Go-Live
System Test
UAT
Data Migration from WSS to Bloomberg AIM Prod Environment
Go-live
2. Request for Proposal (RFP)
[13 empty] | 2. Request for Proposal (RFP) |  |  | 2. Screening of the approved vendor for the Development of the Accounting Module |  |  | 1. Solution Design |  |  | 1. Solution Development
[9 empty] | Request for Proposal (RFP) | [9 empty] | 2. Solution Development | [5 empty] | 1. Solution Development | [5 empty] | 1. UAT |  |  | 1. Data Migration
[9 empty] | Screening of the approved vendor for the Development of the Accounting Module | [15 empty] | 2. System Test | [5 empty] | 2. Data Migration |  |  | 2. Go-Live
Solution Design
Solution Development
System Test
UAT
Data Migration
Go-live
Post Go-live Support
AMD | Development of an Accounting Solution (RED, FMD, & BKSD) | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  | 2026-01-01 | 6/30/2026 | Review &amp; Sign-off Project documents. | Review &amp; Sign-off Project documents. | 10% |  | Development (For CBN Staff only). | 10% | 10% | Analysis and Validation of Business Requirements | 10% | 10% | Evaluation and build of accounting software | 15% | 15% | Evaluation and build of accounting software | 15% | 15% | Integration of feed and transaction from Bloomberg AIM | 15% | 0% | Review and Unit Testing | 10% | 0% | Testing all functionalities according to requirements by end users (System test &amp; UAT) | 10% | 0% | Quality Assurance (by selected CBN Team Leads) | 5% | 0% |  | 0% | 0% |  | 0% | 0% |  | 0% | 0% |  | TRUE | 2025 | =100% OK | 60%
[9 empty] | Validation of Project Scope &amp; Schedule. | Validation of Project Scope &amp; Schedule. |  |  | Requirements Consolidation &amp; Alignment for Accounting Module Development (For CBN Staff). | [5 empty] | Solution Design for the Interface between T24 &amp; Bloomberg AIM |  |  | Solution Design for the Interface between T24 &amp; Bloomberg AIM |  |  | Data Migration &amp; Reconciliation |  |  | Fixing Issues Identified during Unit Testing |  |  | Testing by all Business Users |  |  | Fixing Issues Identified During User Acceptance Testing
[9 empty] | Preparation of pre-requisite resources (E.g., development environment, project team, etc.) | Preparation of pre-requisite resources (E.g., development environment, project team, etc.) | [5 empty] | Handing Over of development environment to iNTEGRA Team | [14 empty] | Feedback from User Acceptance Testing
[9 empty] | Processes Walkthrough for Accounting Module Development (For CBN Staff only). | Processes Walkthrough for Accounting Module |  |  | Project Plan Development and Documentation Workshop (with Vendor) | [20 empty] | Sign Off on Testing
[9 empty] | Requirements Consolidation &amp; Alignment for Accounting Module Development (For CBN Staff). | [24 empty] | Implementation procedure
[9 empty] | Project Plan Development and Documentation Workshop (with Vendor) | [24 empty] | Go-Live
[9 empty] | Analysis and Validation of Business Requirements | [24 empty] | Post Go-Live Support
Handing Over of development environment to iNTEGRA Team.
Evaluation and build of accounting software
Solution Design for the Interface between T24 &amp; Bloomberg AIM
Integration of feed and transaction from Bloomberg AIM
Data Migration &amp; Reconciliation
Review and Unit Testing
Fixing Issues Identified during Unit Testing
Testing all functionalities according to requirements by end users (System test &amp; UAT)
Testing by all Business Users
Feedback from User Acceptance Testing
Quality Assurance (by selected CBN Team Leads)
Fixing Issues Identified During User Acceptance Testing
Sign Off on Testing
Implementation procedure
Go-Live
Post Go-Live Support
AMD | Internet Banking Project | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | 1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | R25 Upgrade | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  |  |  | 1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | New CBA | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | 1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | eBond Phase2 | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"]
AMD | Trade Finance | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Adopt and Adapt digital transformation to optimize costs and improve productivity | ["20% Efficiency of Central Banking Process"] |  |  |  | 1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | FX Inflow Stability for ISO20022 | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | 1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | RevOps | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | 1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | Remita Interface Enhancement | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | 1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live
AMD | NIP Optimization | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  | 2026-07-01 | 2026-12-01 | 1. Requirement Ellicitation | [18 empty] | 1. Requirement Ellicitation | 20 |  | Solution Developement | 25 |  | System Test | 15 |  | Users Training | 10 |  | Deployement to Production | 20 |  | Go Live Support | 10
[9 empty] | 2. Solution Developement | [18 empty] | 2. Solution Developement |  |  | Unit Testing |  |  | Users Training |  |  | Users Accaeptance Test (UAT) |  |  | Pilot Run
[9 empty] | 3. Integration of Componets and Interfaces to ERP | [30 empty] | Go Live
3. Unit Testing
4. System Test
5. Users Training
6. Users Accaeptance Test (UAT)
7. Deployement to Production
8. Pilot Run
9. Go Live
AMD | BN Automation | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | "1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live"
AMD | FCY IN-COUNTRY CLEARING AND SETTLEMENT |  | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | Secure Management Approval | Secure Management Approval |  |  | Document requirement |  |  | System Test
[9 empty] | Document requirement | Document requirement |  |  | Solution Architecture |  |  | Users Accaeptance Test (UAT)
[9 empty] | Solution Architecture | Solution Architecture |  |  | Solution Design |  |  | Deployement to Production
[9 empty] | Solution Design |  |  |  | Solution Developement |  |  | Go Live
[9 empty] | Solution Developement |  |  |  | Unit Testing
Unit Testing
Development and Integration of Componets and Interfaces.
Progress Demonstartion to Stakeholders.
System Test.
Documetation of Technical and Users Mannual.
Users and System support Training.
Users Accaeptance Test (UAT)
Deployement to Production
Go Live
AMD | OMO phase2 | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Ensure payment and regulatory applications efficiency through quality of coding practises | ["20% Efficiency of Central Banking Process"] |  |  |  | "1. Secure Management Approval
2. Document requirement
3. Solution Architecture
4. Solution Design
5. Solution Developement
6. Development and Integration of Componets and Interfaces.
7. Progress Demonstartion to Stakeholders.
8. Unit Testing
9. System Test.
10. Documetation of Technical and Users Mannual.
11. Users and System support Training.
12. Users Accaeptance Test (UAT)
13. Deployement to Production
14. Go Live"
AMD | API Gateway | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | API Modernization & Platform Consolidation | ["None"] |  | 2026-02-01 | 11/30/2026 |  | Conduct platform baseline assessment of existing API Gateway | 10% |  | Build out core gateway clusters (Development + UAT) | 10% | 0% | Roll out rate-limiting, throttling, QoS & plan-based usage control | 10% | 0% | Set up Developer Portal (self-service onboarding + API Catalog) | 15% | 0% | Configure multi-tenant onboarding pipeline | 15% | 0% | User Acceptance Testing (Business, Security, DevOps) | 10% | 0% | Rollout of Analytics & Monetization Engine | 10% | 0% | Internal & external developer onboarding (Tier 1 partners) | 8% | 0% | API lifecycle automation for publishing, rollback & retirements | 5% | 0% | Production rollout preparation | 3% | 0% | Production Deployment | 2% | 0% | End-of-year reporting & KPI closure | 2% | 0% |  | TRUE | 2026 | 100% | 0%
[9 empty] | Conduct platform baseline assessment of existing API Gateway | [18 empty] | (usage reporting, SLA tracking, chargeback models)
[9 empty] | Define service mesh & API lifecycle governance requirements | Document CGate Scale-Out Architecture |  |  | Implement authentication layer (OIDC, OAuth2, PKI Integration) |  |  | Implement API Versioning & Deprecation lifecycle |  |  | Create automated SDK generation (Go, NodeJS, Java, Python) |  |  | Integrate CGate with existing CBN API ecosystem |  |  | Penetration Testing (Internal + External) | [5 empty] | Publish API Documentation & Playbooks | [5 empty] | Governance Approval: Security, Compliance, BRMD |  |  | Cut-over plan execution |  |  | Post-implementation review
[9 empty] | Build out core gateway clusters (Development + UAT) | [18 empty] | Integration with centralized billing modules
[9 empty] | Implement authentication layer (OIDC, OAuth2, PKI Integration) | Define API lifecycle governance requirements |  |  | Configure centralized logging & observability stack |  |  | Enable Dynamic API Policies (Rulesets, Transformations, ABAC Hooks) |  |  | Implement test harnesses for mock endpoints |  |  | Establish security policies: WAF rules, Schema Validation, MTLS |  |  | Performance & Load Testing (100k RPS Target) | [5 empty] | Conduct DevRel Workshops & Sandbox Activation | [5 empty] | Stabilization tuning (caching, rerouting, balancers) |  |  | Monitoring, bug fixing & optimization |  |  | Sustainability & hand-over documentation
Configure centralized logging & observability stack
Roll out rate-limiting, throttling, QoS & plan-based usage control
Implement API Versioning & Deprecation lifecycle
Enable Dynamic API Policies (Rulesets, Transformations, ABAC Hooks)
Set up Developer Portal (self-service onboarding + API Catalog)
Create automated SDK generation (Go, NodeJS, Java, Python)
Implement test harnesses for mock endpoints
Configure multi-tenant onboarding pipeline
Integrate CGate with existing CBN API ecosystem
Establish security policies: WAF rules, Schema Validation, MTLS
User Acceptance Testing (Business, Security, DevOps)
Penetration Testing (Internal + External)
Performance & Load Testing (100k RPS Target)
Rollout of Analytics & Monetization Engine
(usage reporting, SLA tracking, chargeback models)
Integration with centralized billing modules
Internal & external developer onboarding (Tier 1 partners)
Publish API Documentation & Playbooks
Conduct Workshops & Sandbox Activation
API lifecycle automation for publishing, rollback & retirements
Production rollout preparation
Governance Approval: Security, Compliance, BRMD
Stabilization tuning (caching, rerouting, balancers)
Production Deployment
Cut-over plan execution
Monitoring, bug fixing & optimization
End-of-year reporting & KPI closure
Post-implementation review
Sustainability & hand-over documentation
AMD | API Manager Portal | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Strengthened API Governance & Lifecycle Management | ["None"] |  | 2026-01-04 | 11/30/2026 | Requirements gathering & baseline assessment of current API lifecycle processes | Requirements gathering & baseline assessment of current API lifecycle processes | 10% |  | Implement core backend for API lifecycle orchestration | 10% | 0% | Build API approval workflows & policy engines | 10% | 0% | Build admin UI dashboard (API catalog, governance insights, audit trail) | 10% | 0% | Onboard API Providers (internal teams & business units) | 10% | 0% | System & user acceptance testing | 15% | 0% | Configure analytics dashboards (API performance, errors, usage patterns) | 5% | 0% | Full internal onboarding for API stewards, reviewers, service owners | 10% | 0% | Evaluate governance effectiveness (API quality score, review duration, defects) | 5% | 0% | Production rollout preparation | 5% | 0% | Production Deployment | 5% | 0% | Post Implementation Review | 5% | 0% |  | TRUE | 2026 | 100% | 0%
Define governance rules: onboarding, approval stages, versioning, deprecation
[9 empty] | Design API Manager Portal architecture (admin console, governance engine, audit) | Define governance rules: onboarding, approval stages, versioning, deprecation |  |  | Develop authentication & RBAC for Administrators, Reviewers & Publishers |  |  | Implement API change-request pipeline (Create, Modify, Deprecate, Retire) |  |  | Create API traceability modules (ownership, usage, SLA mapping) |  |  | API Documentation standardization (OpenAPI 3.0 / AsyncAPI) |  |  | Security assessment (RBAC, audit logging integrity, workflow abuses) |  |  | Implement automated audit and compliance summaries |  |  | Publish governance playbooks, workflow guides & portal documentation | [5 empty] | Compliance validation (Security, BRMD, Internal Audit) |  |  | Post-deployment monitoring, bug fixing, fine tuning |  |  | Governance sustainability plan & roadmap for 2027
Implement core backend for API lifecycle orchestration
[9 empty] | Develop authentication & RBAC for Administrators, Reviewers & Publishers | Design API Manager Portal architecture (admin console, governance engine, audit) |  |  | Set up service registry integration (existing and new API endpoints) |  |  | Integrate with CGate for policy enforcement hooks |  |  | Implement interactive policy builder (schema validation, transformations) |  |  | Configure governance review SLAs, compliance checks, risk scoring |  |  | Integration with CBN Master Data Directory & Identity Manager |  |  | Connect monetization & costing indicators (if applicable) |  |  | Conduct API lifecycle governance training workshops | [5 empty] | Final stabilization, load tests & configuration optimization |  |  | Service handover to operations team
Set up service registry integration (existing and new API endpoints)
Build API approval workflows & policy engines
Implement API change-request pipeline (Create, Modify, Deprecate, Retire)
Integrate with CGate for policy enforcement hooks
Build admin UI dashboard (API catalog, governance insights, audit trail)
Create API traceability modules (ownership, usage, SLA mapping)
Implement interactive policy builder (schema validation, transformations)
Onboard API Providers (internal teams & business units)
API Documentation standardization (OpenAPI 3.0 / AsyncAPI)
Configure governance review SLAs, compliance checks, risk scoring
System & user acceptance testing
Security assessment (RBAC, audit logging integrity, workflow abuses)
Integration with CBN Master Data Directory & Identity Manager
Configure analytics dashboards (API performance, errors, usage patterns)
Implement automated audit and compliance summaries
Connect monetization & costing indicators (if applicable)
Full internal onboarding for API stewards, reviewers, service owners
Publish governance playbooks, workflow guides & portal documentation
Conduct API lifecycle governance training workshops
Failover testing & API rollback automation
Evaluate governance effectiveness (API quality score, review duration, defects)
Production rollout preparation
Compliance validation (Security, BRMD, Internal Audit)
Final stabilization, load tests & configuration optimization
Production Deployment
Post-deployment monitoring, bug fixing, fine tuning
Service handover to operations team
Year-end reporting and KPI closure
Post Implementation Review
Governance sustainability plan & roadmap for 2027
AMD | Upgrade of SOA Application from 12.2.1.4.0 to 14.1.2 Version | ECBO 2 - Build and sustain excellence in the delivery of all activities, processes and actions of the Bank. | Enhance efficiency in Information Technology Services delivery | Modernization of Integration Middleware & Enterprise Services |  |  | 2026-02-01 | 2026-11-30 | Conduct comprehensive baseline assessment of current SOA 12.2.1.4.0 | Conduct comprehensive baseline assessment of current SOA 12.2.1.4.0 | 10% |  | Build and configure new SOA 14.1.2 environments (DEV + TEST) | 10% | 0% | Migrate composites to 14.1.2 environment | 10% | 0% | Refactor incompatibilities & fix compile-time errors | 10% | 0% | System Integration Testing (SIT) for all migrated composites | 15% | 0% | UAT with business stakeholders & consuming applications | 10% | 0% | Load & stress testing (simulate enterprise transaction volumes) | 10% | 0% | Prepare Production deployment plan & rollback strategy | 5% | 0% | Execute dry-run migration (pre-production environment) | 5% | 0% | Production readiness: security, audit, BRMD, compliance clearance | 5% | 0% | Production Deployment of SOA 14.1.2 | 5% | 0% | Post Implementation Review | 5% | 0% |  | TRUE | 2026 | 100% | 0%
Inventory composites, adapters, partners, service dependencies
[9 empty] | Draft upgrade readiness report & risk register | Inventory composites, adapters, partners, service dependencies |  |  | Configure WebLogic domain upgrades, clusters & JVM tuning |  |  | Resolve deprecated APIs, adapters & integration patterns |  |  | Rewrite/modernize deprecated integrations (file, JDBC, SOAP, REST adapters) |  |  | Regression testing for enterprise integrations |  |  | End-to-end integration testing with ESB, API Gateway, CBS, ERP |  |  | Benchmark comparison between 12c and 14c environments |  |  | Create cut-over sequencing for integrations, adapters & composites |  |  | Validate configuration, endpoints, JMS stores, error handlers |  |  | Stabilization & correction of environment-level issues |  |  | Hypercare support & issue resolution |  |  | Build sustainability roadmap & transition documents
Build and configure new SOA 14.1.2 environments (DEV + TEST)
[9 empty] | Configure WebLogic domain upgrades, clusters & JVM tuning | Draft upgrade readiness report & risk register | [5 empty] | Update shared libraries, JCA connections & binding properties |  |  | Implement migration automation scripts |  |  | Validate performance baselines (latency, throughput, timeouts) |  |  | Security validations (privileges, tokens, access policies) |  |  | Performance tuning based on findings |  |  | Conduct business continuity review (DR/Failover tests) |  |  | Finalize go/no-go report |  |  | Ensure backup, retention & operational playbooks updated |  |  | Performance monitoring & final optimization
Migrate composites to 14.1.2 environment
Resolve deprecated APIs, adapters & integration patterns
Update shared libraries, JCA connections & binding properties
Refactor incompatibilities & fix compile-time errors
Rewrite/modernize deprecated integrations (file, JDBC, SOAP, REST adapters)
Implement migration automation scripts
System Integration Testing (SIT) for all migrated composites
Regression testing for enterprise integrations
Validate performance baselines (latency, throughput, timeouts)
UAT with business stakeholders & consuming applications
End-to-end integration testing with ESB, API Gateway, CBS, ERP
Security validations (privileges, tokens, access policies)
Load & stress testing (simulate enterprise transaction volumes)
Benchmark comparison between 12c and 14c environments
Performance tuning based on findings
Prepare Production deployment plan & rollback strategy
Create cut-over sequencing for integrations, adapters & composites
Conduct business continuity review (DR/Failover tests)
Exeute dry-run migration (pre-production environment)
Validate configuration, endpoints, JMS stores, error handlers
Finalize go/no-go report
Production readiness: security, audit, BRMD, compliance clearance
Stabilization & correction of environment-level issues
Ensure backup, retention & operational playbooks updated
Production Deployment of SOA 14.1.2
Hypercare support & issue resolution
Performance monitoring & final optimization
Post Implementation Review
KPI Closure & Year-End Reporting
Build sustainability roadmap & transition documents