## Task Dashboard
Central Bank of Nigeria ENTERPRISE SERVICE MANAGEMENT SOLUTION
Project Task Register — Executive Summary Dashboard
Document Ref: ITD/BRM/CON/BRD/01/148 ¦ Version 1.0 ¦ Classification: Confidential
Work Stream | Total Tasks | Critical | High | Medium | Low | Estimated Effort (Person-Days) | Assigned To | Phase
WS-01: Project Governance & Planning | 18 | 2 | 8 | 6 | 2 | 45 | Project Manager | Phase 0
WS-02: Requirements & Design | 24 | 4 | 12 | 6 | 2 | 60 | Business Analyst / Architect | Phase 1
WS-03: CMDB & Asset Management | 32 | 6 | 16 | 8 | 2 | 90 | CMDB Lead / Backend Dev | Phase 1
WS-04: Incident Management Module | 21 | 2 | 10 | 7 | 2 | 50 | Service Desk Lead | Phase 1
WS-05: Problem Management Module | 14 | 2 | 6 | 4 | 2 | 35 | Problem Manager / Dev | Phase 1
WS-06: Change Management Module | 18 | 4 | 8 | 4 | 2 | 48 | Change Manager / Dev | Phase 1
WS-07: Request Fulfillment & Service Catalog | 18 | 2 | 8 | 6 | 2 | 42 | Service Catalog Owner | Phase 1
WS-08: Knowledge Management | 16 | 1 | 7 | 6 | 2 | 38 | KM Lead / Content Dev | Phase 2
WS-09: SLA & Reporting Engine | 16 | 2 | 8 | 4 | 2 | 40 | SLA Manager / BI Dev | Phase 2
WS-10: Security & Compliance | 27 | 6 | 14 | 5 | 2 | 55 | Security Architect | Phase 1
WS-11: Integration (AD, Teams, SSO, EA, SCCM) | 16 | 4 | 8 | 3 | 1 | 45 | Integration Lead | Phase 2
WS-12: UI/UX & Platform Config | 12 | 1 | 5 | 4 | 2 | 30 | Frontend Lead / UX | Phase 1
WS-13: Infrastructure & HA/DR | 14 | 4 | 6 | 3 | 1 | 38 | Infrastructure Lead | Phase 1
WS-14: Testing & QA | 22 | 4 | 10 | 6 | 2 | 55 | QA Lead / Test Manager | Phase 3
WS-15: Data Migration & Cutover | 12 | 4 | 6 | 2 | 0 | 30 | Migration Lead | Phase 3
WS-16: Training & Change Management | 14 | 2 | 6 | 4 | 2 | 35 | Training Lead / PM | Phase 4
WS-17: Go-Live & Post-Implementation | 10 | 2 | 4 | 3 | 1 | 25 | Delivery Manager | Phase 5
GRAND TOTAL | 304 | 52 | 142 | 81 | 29 | 761
© Information Technology Department, Central Bank of Nigeria ¦ Classified as Confidential

## Full Task Register
Central Bank of Nigeria ENTERPRISE SERVICE MANAGEMENT SOLUTION
Project Task Register — Full Work Breakdown Structure (304 Tasks)
Document Ref: ITD/BRM/CON/BRD/01/148 ¦ Version 1.0 ¦ Classification: Confidential
Task ID | Work Stream | WBS Ref | Task Description | Task Type | Priority | RTM Req Trace | BRD Section | Module/Component | Deliverable | Assigned Role | Assigned To | Phase | Est. Effort (PD) | Start Date | End Date | Dependencies | Status | % Complete | Remarks
TSK-0001 | WS-01: Governance & Planning | 1.1.1 | Project charter and mandate documentation | Governance | Critical | BR-001 to BR-012 | §1.0-§3.0 | PMO | Project Charter Document | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0002 | WS-01: Governance & Planning | 1.1.2 | Establish project governance structure (Steering Committee, PMO, workstreams) | Governance | High | All | §4.0 | PMO | Governance Framework | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0003 | WS-01: Governance & Planning | 1.1.3 | Develop detailed project plan with milestones and critical path | Planning | High | All | §5.0 | PMO | Project Plan (MS Project/Gantt) | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0004 | WS-01: Governance & Planning | 1.1.4 | Define RACI matrix for all workstreams | Planning | High | All | §4.0 | PMO | RACI Matrix | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0005 | WS-01: Governance & Planning | 1.1.5 | Establish communication plan (status reporting cadence, stakeholder comms) | Planning | Medium | All | §4.0 | PMO | Communication Plan | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0006 | WS-01: Governance & Planning | 1.1.6 | Define risk management framework and risk register | Governance | High | All | §3.0 | PMO | Risk Register | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0007 | WS-01: Governance & Planning | 1.1.7 | Vendor evaluation criteria definition and scoring matrix | Procurement | Critical | BR-005 | §3.0 | PMO | Vendor Evaluation Matrix | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0008 | WS-01: Governance & Planning | 1.1.8 | Vendor shortlisting and technical evaluation | Procurement | High | All | §3.0 | PMO | Vendor Evaluation Report | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0009 | WS-01: Governance & Planning | 1.1.9 | Vendor selection and contract negotiation | Procurement | High | All | §3.0 | PMO | Contract/SLA Document | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0010 | WS-01: Governance & Planning | 1.1.10 | Define project scope baseline and change control process | Governance | High | All | §5.0 | PMO | Scope Baseline Document | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0011 | WS-01: Governance & Planning | 1.1.11 | Budget planning and cost estimation (TCO analysis) | Planning | High | BR-005 | §3.0 | PMO | Budget Estimate | Finance/PM | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0012 | WS-01: Governance & Planning | 1.1.12 | License procurement planning (575+ licenses) | Procurement | High | GEN-FR004 | §5.0 | PMO | License Plan | Procurement Lead | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0013 | WS-01: Governance & Planning | 1.1.13 | Stakeholder engagement plan and sign-off schedule | Planning | Medium | All | §4.0 | PMO | Stakeholder Plan | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0014 | WS-01: Governance & Planning | 1.1.14 | Quality management plan | Planning | Medium | All | §3.0 | PMO | QM Plan | QA Lead | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0015 | WS-01: Governance & Planning | 1.1.15 | Define project KPIs and success criteria | Planning | Medium | All | §3.0 | PMO | KPI Framework | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0016 | WS-01: Governance & Planning | 1.1.16 | Weekly/fortnightly status reporting template and cadence | Governance | Low | All | §4.0 | PMO | Status Report Template | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0017 | WS-01: Governance & Planning | 1.1.17 | Issue and decision log setup | Governance | Low | All | — | PMO | Issue/Decision Log | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0018 | WS-01: Governance & Planning | 1.1.18 | Project kick-off meeting and workshop | Planning | High | All | §1.0 | PMO | Kick-off Pack | Project Manager | TBD | Phase 0 | 3 |  |  |  | Not Started | 0%
TSK-0019 | WS-02: Requirements & Design | 2.1.1 | Validate and baseline all 234 requirements from BRD with stakeholders | Requirements | Critical | All | §8.0 | Requirements | Validated RTM | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0020 | WS-02: Requirements & Design | 2.1.2 | Conduct requirements gap analysis against selected vendor solution | Requirements | Critical | All | §8.0 | Requirements | Gap Analysis Report | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0021 | WS-02: Requirements & Design | 2.1.3 | Define detailed functional specification for CMDB module | Design | High | CMDB-FR001 to FR032 | §6.9 | CMDB | CMDB Functional Spec | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0022 | WS-02: Requirements & Design | 2.1.4 | Define detailed functional specification for Incident Management | Design | High | INC-FR001 to FR021 | §6.3 | Incident Mgmt | Incident Mgmt Spec | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0023 | WS-02: Requirements & Design | 2.1.5 | Define detailed functional specification for Problem Management | Design | High | PM-FR001 to FR011 | §6.2 | Problem Mgmt | Problem Mgmt Spec | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0024 | WS-02: Requirements & Design | 2.1.6 | Define detailed functional specification for Change Management | Design | Critical | CHG-FR001 to FR012 | §6.4 | Change Mgmt | Change Mgmt Spec | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0025 | WS-02: Requirements & Design | 2.1.7 | Define detailed functional specification for Request Fulfillment | Design | High | REQ-FR001 to FR015 | §6.1 | Request Fulfillment | Request Fulfillment Spec | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0026 | WS-02: Requirements & Design | 2.1.8 | Define detailed functional specification for Knowledge Management | Design | High | KM-* | §8.2 | Knowledge Mgmt | KM Spec | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0027 | WS-02: Requirements & Design | 2.1.9 | Define detailed functional specification for SLA Management | Design | High | SLM-FR001 to FR011 | §8.2 | SLA Mgmt | SLA Mgmt Spec | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0028 | WS-02: Requirements & Design | 2.1.10 | Define reporting requirements specification (dashboards, KPIs, MTTR) | Design | High | RPT-UR001 to UR008 | §8.3 | Reporting | Reporting Spec | BI Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0029 | WS-02: Requirements & Design | 2.1.11 | Enterprise Architecture design (HLD) – all modules | Design | Critical | All | §6.0-§9.0 | Architecture | High-Level Design Document | Enterprise Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0030 | WS-02: Requirements & Design | 2.1.12 | Detailed technical design (LLD) – application tier | Design | High | All | §9.0 | Architecture | Low-Level Design Document | Solution Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0031 | WS-02: Requirements & Design | 2.1.13 | Database schema design for CMDB and all ITSM modules | Design | High | CMDB-FR006 | §6.9 | Data Layer | DB Schema Document | DB Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0032 | WS-02: Requirements & Design | 2.1.14 | Integration architecture design (AD, Teams, SSO, MEGA EA, SCCM, Oracle ERP) | Design | High | GEN-FR017, IR001, IR002 | §9.9 | Integration | Integration Architecture Doc | Integration Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0033 | WS-02: Requirements & Design | 2.1.15 | Security architecture design (RBAC, MFA, encryption, SIEM) | Design | Critical | SEC-SR001 to SR027 | §9.1 | Security | Security Architecture Doc | Security Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0034 | WS-02: Requirements & Design | 2.1.16 | HA/DR architecture design (99.9%-99.999% availability) | Design | High | BC001, AR001, DR001 | §9.4-§9.11 | Infrastructure | HA/DR Design Document | Infrastructure Architect | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0035 | WS-02: Requirements & Design | 2.1.17 | UI/UX wireframes and prototype for key user journeys | Design | Medium | GEN-FR001, OR010 | §9.2 | UI/UX | Wireframes/Prototype | UX Designer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0036 | WS-02: Requirements & Design | 2.1.18 | Workflow design for all 8 ITIL processes (to-be) | Design | High | All process flows | §6.0 | Workflow Engine | Workflow Design Pack | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0037 | WS-02: Requirements & Design | 2.1.19 | Define data migration strategy (CI data from Excel to CMDB) | Design | High | CMDB-FR009 | §6.9 | CMDB | Data Migration Strategy | Migration Lead | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0038 | WS-02: Requirements & Design | 2.1.20 | Define naming convention standards for CIs | Design | Medium | CMDB-FR001 | §8.2 | CMDB | CI Naming Convention Doc | CMDB Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0039 | WS-02: Requirements & Design | 2.1.21 | Service catalog design (hierarchical structure, categories) | Design | Medium | REQ-FR010 to FR015 | §8.2 | Service Catalog | Service Catalog Design | Service Catalog Owner | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0040 | WS-02: Requirements & Design | 2.1.22 | SLA/OLA/UC definitions and threshold design | Design | Medium | SLM-FR001 to FR011 | §8.2 | SLA Mgmt | SLA Definition Pack | SLA Manager | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0041 | WS-02: Requirements & Design | 2.1.23 | Email template design for ticket creation (ithelpdesk@cbn.gov.ng) | Design | Medium | GEN-FR011 | §8.2 | General | Email Template Specs | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0042 | WS-02: Requirements & Design | 2.1.24 | Design review and sign-off by all stakeholder divisions | Governance | High | All | §4.0 | All | Signed Design Documents | Project Manager | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0043 | WS-03: CMDB & Asset Mgmt | 3.1.1 | Configure CMDB core database schema and CI types | Build | Critical | CMDB-FR006, FR028 | §6.9 | CMDB | Configured CMDB Schema | CMDB Lead | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0044 | WS-03: CMDB & Asset Mgmt | 3.1.2 | Configure CI naming convention and auto-numbering | Build | High | CMDB-FR001 | §8.2 | CMDB | CI Naming Rules | CMDB Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0045 | WS-03: CMDB & Asset Mgmt | 3.1.3 | Configure Service Asset record types and attributes | Build | High | CMDB-FR002, FR022 | §8.2 | CMDB | Asset Record Types | CMDB Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0046 | WS-03: CMDB & Asset Mgmt | 3.1.4 | Configure CI status workflow (lifecycle states) | Build | High | CMDB-FR003 | §8.2 | CMDB | CI Status Workflow | CMDB Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0047 | WS-03: CMDB & Asset Mgmt | 3.1.5 | Configure CI relationship model (parent/child, depends-on, runs-on) | Build | Critical | CMDB-FR004, FR019, FR021 | §8.2 | CMDB | Relationship Model | CMDB Lead | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0048 | WS-03: CMDB & Asset Mgmt | 3.1.6 | Build CI relationship auto-management (auto re-establish on CRUD) | Build | High | CMDB-FR019, FR030 | §8.2 | CMDB | Auto-Relationship Engine | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0049 | WS-03: CMDB & Asset Mgmt | 3.1.7 | Configure CI attribute recording and validation rules | Build | High | CMDB-FR022 | §8.2 | CMDB | Attribute Rules | CMDB Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0050 | WS-03: CMDB & Asset Mgmt | 3.1.8 | Build CI graphical topology/relationship viewer | Build | High | CMDB-FR014 | §8.2 | CMDB | Topology Viewer | Frontend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0051 | WS-03: CMDB & Asset Mgmt | 3.1.9 | Configure IP-range network discovery engine | Build | Critical | CMDB-FR015, FR027 | §8.2 | CMDB | Discovery Configuration | Network Engineer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0052 | WS-03: CMDB & Asset Mgmt | 3.1.10 | Configure automatic application connection detection | Build | High | CMDB-FR016 | §8.2 | CMDB | App Discovery Rules | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0053 | WS-03: CMDB & Asset Mgmt | 3.1.11 | Build discovery-to-CMDB reconciliation engine | Build | Critical | CMDB-FR017 | §6.9 | CMDB | Reconciliation Engine | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0054 | WS-03: CMDB & Asset Mgmt | 3.1.12 | Build production environment auto-sync for CM updates | Build | High | CMDB-FR018 | §8.2 | CMDB | Production Sync Module | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0055 | WS-03: CMDB & Asset Mgmt | 3.1.13 | Configure CI change history logging and audit trail | Build | High | CMDB-FR007, FR020, FR031 | §8.2 | CMDB | Audit Trail Config | CMDB Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0056 | WS-03: CMDB & Asset Mgmt | 3.1.14 | Configure strict access control on all CIs | Build | Critical | CMDB-FR008 | §8.2 | CMDB | CI Access Control | Security Lead | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0057 | WS-03: CMDB & Asset Mgmt | 3.1.15 | Build complete IT asset inventory module (full lifecycle) | Build | High | CMDB-FR009 | §6.8 | CMDB | Asset Inventory Module | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0058 | WS-03: CMDB & Asset Mgmt | 3.1.16 | Build CI update/editor interface | Build | Medium | CMDB-FR010 | §8.2 | CMDB | CI Editor UI | Frontend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0059 | WS-03: CMDB & Asset Mgmt | 3.1.17 | Build comprehensive CI inventory reporting (items, attributes, links) | Build | High | CMDB-FR011 | §8.2 | CMDB | CI Report Templates | BI Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0060 | WS-03: CMDB & Asset Mgmt | 3.1.18 | Build Service Asset reporting with financial info | Build | High | CMDB-FR012 | §8.2 | CMDB | Asset Financial Reports | BI Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0061 | WS-03: CMDB & Asset Mgmt | 3.1.19 | Build change impact analysis module (what CIs affected by change) | Build | Critical | CMDB-FR013, FR025 | §8.2 | CMDB | Impact Analysis Module | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0062 | WS-03: CMDB & Asset Mgmt | 3.1.20 | Build automated CI data verification against physical infrastructure | Build | High | CMDB-FR023, FR032 | §8.2 | CMDB | Physical Verification Engine | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0063 | WS-03: CMDB & Asset Mgmt | 3.1.21 | Build CI customizable relationship model designer | Build | Medium | CMDB-FR021, FR029 | §8.2 | CMDB | Model Designer UI | Frontend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0064 | WS-03: CMDB & Asset Mgmt | 3.1.22 | Configure CMDB federation (import server, staging area) | Build | High | All CMDB | §6.9 | CMDB | Federation Config | CMDB Lead | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0065 | WS-03: CMDB & Asset Mgmt | 3.1.23 | Configure CMDB synchronization rules | Build | High | All CMDB | §6.9 | CMDB | Sync Rules | CMDB Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0066 | WS-03: CMDB & Asset Mgmt | 3.1.24 | Build CMDB variance comparison reporting | Build | Medium | All CMDB | §6.9 | CMDB | Variance Reports | BI Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0067 | WS-03: CMDB & Asset Mgmt | 3.1.25 | Configure asset deployment workflow (request→approve→issue→configure→deploy) | Build | High | All Asset | §6.8 | Asset Mgmt | Deploy Workflow | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0068 | WS-03: CMDB & Asset Mgmt | 3.1.26 | Configure asset redeployment workflow (exit/transfer) | Build | Medium | All Asset | §6.8 | Asset Mgmt | Redeploy Workflow | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0069 | WS-03: CMDB & Asset Mgmt | 3.1.27 | Configure asset maintenance workflow (warranty, 3rd party, stop-gap) | Build | Medium | All Asset | §6.8 | Asset Mgmt | Maintenance Workflow | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0070 | WS-03: CMDB & Asset Mgmt | 3.1.28 | Configure asset retirement/disposal workflow (degauss, dispose) | Build | Medium | All Asset | §6.8 | Asset Mgmt | Retirement Workflow | Business Analyst | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0071 | WS-03: CMDB & Asset Mgmt | 3.1.29 | Build asset management reporting (status reports, management reports) | Build | Medium | All Asset | §6.8 | Asset Mgmt | Asset Reports | BI Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0072 | WS-03: CMDB & Asset Mgmt | 3.1.30 | CMDB unit testing | Testing | High | All CMDB | §6.6 | CMDB | Test Results | QA Engineer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0073 | WS-03: CMDB & Asset Mgmt | 3.1.31 | CMDB integration testing with all ITSM modules | Testing | Critical | MR001 | §6.7 | CMDB | Integration Test Report | QA Lead | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0074 | WS-03: CMDB & Asset Mgmt | 3.1.32 | CMDB discovery testing (network scan validation) | Testing | High | CMDB-FR015 | §6.7 | CMDB | Discovery Test Report | Network Engineer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0075 | WS-04: Incident Management | 4.1.1 | Configure incident record CRUD operations | Build | High | INC-FR001 | §6.3 | Incident Mgmt | Incident CRUD Config | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0076 | WS-04: Incident Management | 4.1.2 | Configure free text fields for description and resolution | Build | Medium | INC-FR002 | §6.3 | Incident Mgmt | Field Configuration | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0077 | WS-04: Incident Management | 4.1.3 | Configure role-based access for incident records | Build | High | INC-FR003 | §6.3 | Incident Mgmt | RBAC Rules | Security Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0078 | WS-04: Incident Management | 4.1.4 | Build automated incident classification and recording engine | Build | High | INC-FR004 | §6.3 | Incident Mgmt | Auto-Classification | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0079 | WS-04: Incident Management | 4.1.5 | Configure incident status workflow (Open→Assigned→Waiting→OnHold→Resolved→Closed) | Build | Critical | INC-FR005 | §6.3 | Incident Mgmt | Status Workflow | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0080 | WS-04: Incident Management | 4.1.6 | Build incident subtask functionality (assign to different groups) | Build | High | INC-FR006 | §6.3 | Incident Mgmt | Subtask Module | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0081 | WS-04: Incident Management | 4.1.7 | Configure email integration for incident linking | Build | High | INC-FR007 | §6.3 | Incident Mgmt | Email Integration | Integration Dev | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0082 | WS-04: Incident Management | 4.1.8 | Build notification engine (reassignment, comments, status change) | Build | High | INC-FR008, FR009 | §6.3 | Incident Mgmt | Notification Engine | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0083 | WS-04: Incident Management | 4.1.9 | Build KB article linkage from incident screens | Build | Medium | INC-FR010 | §6.3 | Incident Mgmt | KB Linkage | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0084 | WS-04: Incident Management | 4.1.10 | Configure automated escalation thresholds and rules | Build | Critical | INC-FR011 | §6.3 | Incident Mgmt | Escalation Rules | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0085 | WS-04: Incident Management | 4.1.11 | Configure priority/impact/urgency matrix | Build | High | INC-FR012 | §6.3 | Incident Mgmt | Priority Matrix | Business Analyst | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0086 | WS-04: Incident Management | 4.1.12 | Build automated routing/alerting to support groups | Build | High | INC-FR013 | §6.3 | Incident Mgmt | Auto-Routing Engine | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0087 | WS-04: Incident Management | 4.1.13 | Build ticket auto-closure and bulk closure functionality | Build | Medium | INC-FR014 | §6.3 | Incident Mgmt | Auto/Bulk Close | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0088 | WS-04: Incident Management | 4.1.14 | Build incident reporting (outstanding, management, historical) | Build | High | INC-FR015, FR016 | §6.3 | Incident Mgmt | Report Templates | BI Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0089 | WS-04: Incident Management | 4.1.15 | Build secure audit log for all incident updates | Build | High | INC-FR017 | §6.3 | Incident Mgmt | Audit Log | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0090 | WS-04: Incident Management | 4.1.16 | Build document attachment capability (at creation + lifecycle) | Build | Medium | INC-FR018 | §6.3 | Incident Mgmt | Attachment Module | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0091 | WS-04: Incident Management | 4.1.17 | Configure ticket ownership auto-default to resolver | Build | Medium | INC-FR019 | §6.3 | Incident Mgmt | Ownership Rules | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0092 | WS-04: Incident Management | 4.1.18 | Build closed incident search functionality | Build | Medium | INC-FR020 | §6.3 | Incident Mgmt | Search Module | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0093 | WS-04: Incident Management | 4.1.19 | Build incident reopen functionality | Build | Medium | INC-FR021 | §6.3 | Incident Mgmt | Reopen Logic | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0094 | WS-04: Incident Management | 4.1.20 | Configure Major Incident Handling procedure (P1 workflow) | Build | High | INC process §6.3 | §6.3 | Incident Mgmt | Major Incident Workflow | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0095 | WS-04: Incident Management | 4.1.21 | Incident module unit and integration testing | Testing | High | All INC | §6.7 | Incident Mgmt | Test Report | QA Engineer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0096 | WS-05: Problem Management | 5.1.1 | Configure problem record CRUD operations | Build | High | PM-FR001 | §6.2 | Problem Mgmt | Problem CRUD | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0097 | WS-05: Problem Management | 5.1.2 | Build incident/problem/known-error distinction logic | Build | Critical | PM-FR002 | §6.2 | Problem Mgmt | Classification Logic | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0098 | WS-05: Problem Management | 5.1.3 | Build incident-to-problem-to-known-error matching engine | Build | Critical | PM-FR003 | §6.2 | Problem Mgmt | Matching Engine | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0099 | WS-05: Problem Management | 5.1.4 | Configure problem routing to pre-defined support groups | Build | High | PM-FR004 | §6.2 | Problem Mgmt | Routing Rules | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0100 | WS-05: Problem Management | 5.1.5 | Configure impact/urgency coding for problems | Build | High | PM-FR005 | §6.2 | Problem Mgmt | Priority Matrix | Business Analyst | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0101 | WS-05: Problem Management | 5.1.6 | Build problem progress tracking and ownership monitoring | Build | High | PM-FR006 | §6.2 | Problem Mgmt | Tracking Dashboard | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0102 | WS-05: Problem Management | 5.1.7 | Build root cause analysis tooling and impact analysis | Build | High | PM-FR007 | §6.2 | Problem Mgmt | RCA Module | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0103 | WS-05: Problem Management | 5.1.8 | Build Known Error Database (KEDB) with historical data | Build | High | PM-FR008 | §6.2 | Problem Mgmt | KEDB Module | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0104 | WS-05: Problem Management | 5.1.9 | Build trend analysis and customizable management reports | Build | Medium | PM-FR009 | §6.2 | Problem Mgmt | Report Templates | BI Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0105 | WS-05: Problem Management | 5.1.10 | Configure free text for problem descriptions | Build | Low | PM-FR010 | §6.2 | Problem Mgmt | Field Config | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0106 | WS-05: Problem Management | 5.1.11 | Build dynamic severity escalation based on associated incidents | Build | High | PM-FR011 | §6.2 | Problem Mgmt | Auto-Severity Logic | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0107 | WS-05: Problem Management | 5.1.12 | Configure workaround workflow and KEDB update process | Build | Medium | Process §6.2 step 5 | §6.2 | Problem Mgmt | Workaround Workflow | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0108 | WS-05: Problem Management | 5.1.13 | Configure 3rd party escalation workflow | Build | Medium | Process §6.2 step 6 | §6.2 | Problem Mgmt | 3rd Party Workflow | Business Analyst | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0109 | WS-05: Problem Management | 5.1.14 | Problem module unit and integration testing | Testing | High | All PM | §6.7 | Problem Mgmt | Test Report | QA Engineer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0110 | WS-06: Change Management | 6.1.1 | Configure RFC record and lifecycle tracking | Build | Critical | CHG-FR001 | §6.4 | Change Mgmt | RFC Lifecycle Config | ITSM Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0111 | WS-06: Change Management | 6.1.2 | Configure role-based access control for change records | Build | High | CHG-FR002 | §6.4 | Change Mgmt | RBAC Config | Security Lead | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0112 | WS-06: Change Management | 6.1.3 | Build RFC routing to Cat 1/2/3 authorization bodies | Build | Critical | CHG-FR003 | §6.4 | Change Mgmt | Routing Engine | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0113 | WS-06: Change Management | 6.1.4 | Build change rejection workflow with notification | Build | High | CHG-FR004 | §6.4 | Change Mgmt | Rejection Workflow | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0114 | WS-06: Change Management | 6.1.5 | Build impact assessment attachment/recording capability | Build | High | CHG-FR005 | §6.4 | Change Mgmt | Impact Assessment Module | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0115 | WS-06: Change Management | 6.1.6 | Build change schedule production (build/test/implement) | Build | High | CHG-FR006 | §6.4 | Change Mgmt | Change Calendar | Frontend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0116 | WS-06: Change Management | 6.1.7 | Build back-out procedure recording within change record | Build | High | CHG-FR007 | §6.4 | Change Mgmt | Back-out Procedure | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0117 | WS-06: Change Management | 6.1.8 | Build SLA breach notification and escalation for changes | Build | High | CHG-FR008 | §6.4 | Change Mgmt | SLA Alert Engine | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0118 | WS-06: Change Management | 6.1.9 | Build post-implementation review scheduling | Build | Medium | CHG-FR009 | §6.4 | Change Mgmt | PIR Scheduler | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0119 | WS-06: Change Management | 6.1.10 | Build customizable change reporting (multi-field/multi-record) | Build | High | CHG-FR010 | §6.4 | Change Mgmt | Report Builder | BI Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0120 | WS-06: Change Management | 6.1.11 | Build cross-functional impact assessment integration | Build | High | CHG-FR011 | §6.4 | Change Mgmt | Cross-Module Integration | Backend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0121 | WS-06: Change Management | 6.1.12 | Build post-implementation impact identification | Build | Medium | CHG-FR012 | §6.4 | Change Mgmt | PIR Analytics | BI Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0122 | WS-06: Change Management | 6.1.13 | Configure Emergency Change workflow | Build | Critical | Process §6.4 step 2 | §6.4 | Change Mgmt | Emergency Change Flow | ITSM Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0123 | WS-06: Change Management | 6.1.14 | Configure Standard Change workflow (pre-approved) | Build | High | Process §6.4 | §6.4 | Change Mgmt | Standard Change Flow | ITSM Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0124 | WS-06: Change Management | 6.1.15 | Configure Normal Change workflow with CAB integration | Build | Critical | Process §6.4 step 4 | §6.4 | Change Mgmt | Normal Change Flow | ITSM Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0125 | WS-06: Change Management | 6.1.16 | Build CAB meeting scheduler and agenda generator | Build | Medium | Process §6.4 step 4.2 | §6.4 | Change Mgmt | CAB Scheduler | Frontend Developer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0126 | WS-06: Change Management | 6.1.17 | Configure change documentation and close-out process | Build | Medium | Process §6.4 step 6 | §6.4 | Change Mgmt | Close-out Process | ITSM Admin | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0127 | WS-06: Change Management | 6.1.18 | Change module unit and integration testing | Testing | High | All CHG | §6.7 | Change Mgmt | Test Report | QA Engineer | TBD | Phase 1 | 3 |  |  |  | Not Started | 0%
TSK-0128 | WS-07: Request Fulfillment | 7.1.1 | Configure service catalog structure (hierarchical views) | Build | High | REQ-FR010, FR011 | §6.1 | Service Catalog | Catalog Structure | Service Catalog Owner | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0129 | WS-07: Request Fulfillment | 7.1.2 | Build customer-facing request detail display | Build | Medium | REQ-FR001 | §6.1 | Request Fulfillment | Request Detail UI | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0130 | WS-07: Request Fulfillment | 7.1.3 | Build guided service request wizard | Build | Medium | REQ-FR002 | §6.1 | Request Fulfillment | Request Wizard | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0131 | WS-07: Request Fulfillment | 7.1.4 | Build service request form automation with approval workflow | Build | High | REQ-FR003 | §6.1 | Request Fulfillment | Approval Workflow | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0132 | WS-07: Request Fulfillment | 7.1.5 | Build web-based ticket submission and tracking portal | Build | High | REQ-FR004 | §6.1 | Request Fulfillment | Self-Service Portal | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0133 | WS-07: Request Fulfillment | 7.1.6 | Build step-by-step fulfillment activity tracking | Build | High | REQ-FR005 | §6.1 | Request Fulfillment | Fulfillment Tracker | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0134 | WS-07: Request Fulfillment | 7.1.7 | Integrate Request Management with full ITSM suite | Build | High | REQ-FR006 | §6.1 | Request Fulfillment | ITSM Integration | Integration Dev | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0135 | WS-07: Request Fulfillment | 7.1.8 | Build end-user KB access via web front end | Build | Medium | REQ-FR007 | §6.1 | Request Fulfillment | KB Portal | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0136 | WS-07: Request Fulfillment | 7.1.9 | Build search with rating/ranking of KB items | Build | Medium | REQ-FR008 | §6.1 | Request Fulfillment | KB Search Engine | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0137 | WS-07: Request Fulfillment | 7.1.10 | Build attachment add/view capability for end users | Build | Medium | REQ-FR009 | §6.1 | Request Fulfillment | Attachment Module | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0138 | WS-07: Request Fulfillment | 7.1.11 | Build SLA Catalog with service bundles and pricing | Build | High | REQ-FR012 | §6.1 | Service Catalog | SLA Catalog | SLA Manager | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0139 | WS-07: Request Fulfillment | 7.1.12 | Configure service catalog under change management governance | Build | Medium | REQ-FR013 | §6.1 | Service Catalog | Catalog Governance | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0140 | WS-07: Request Fulfillment | 7.1.13 | Build service definition with SLA, billing, contractual templates | Build | High | REQ-FR014 | §6.1 | Service Catalog | Service Definition Module | Business Analyst | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0141 | WS-07: Request Fulfillment | 7.1.14 | Build service element grouping functionality | Build | Medium | REQ-FR015 | §6.1 | Service Catalog | Service Grouping | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0142 | WS-07: Request Fulfillment | 7.1.15 | Configure request fulfillment workflow (13-step process from §6.1) | Build | High | Process §6.1 | §6.1 | Request Fulfillment | Request Workflow | Business Analyst | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0143 | WS-07: Request Fulfillment | 7.1.16 | Configure approval routing (predefined approval process) | Build | High | Process §6.1 step 3 | §6.1 | Request Fulfillment | Approval Routing | ITSM Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0144 | WS-07: Request Fulfillment | 7.1.17 | Configure SLA breach detection and escalation for requests | Build | High | Process §6.1 step 10.2 | §6.1 | Request Fulfillment | SLA Breach Logic | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0145 | WS-07: Request Fulfillment | 7.1.18 | Request fulfillment module testing | Testing | High | All REQ | §6.7 | Request Fulfillment | Test Report | QA Engineer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0146 | WS-08: Knowledge Management | 8.1.1 | Build KB search from incident management screens | Build | High | KM-GEN-FR001 | §8.2 | Knowledge Mgmt | KB Search Integration | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0147 | WS-08: Knowledge Management | 8.1.2 | Build flexible/robust search engine with relevancy algorithm | Build | High | KM-GEN-FR002, KM-SRCH-FR004, FR005 | §8.2 | Knowledge Mgmt | Search Engine | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0148 | WS-08: Knowledge Management | 8.1.3 | Build document linking (internal and external) | Build | Medium | KM-GEN-FR003 | §8.2 | Knowledge Mgmt | Document Linker | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0149 | WS-08: Knowledge Management | 8.1.4 | Build usage/volume/effectiveness reporting | Build | Medium | KM-GEN-FR004 | §8.2 | Knowledge Mgmt | KB Reports | BI Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0150 | WS-08: Knowledge Management | 8.1.5 | Build knowledge distribution tools (print, email, copy, fax) | Build | Medium | KM-GEN-FR005 | §8.2 | Knowledge Mgmt | Distribution Module | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0151 | WS-08: Knowledge Management | 8.1.6 | Build authoring tools with workflow and version control | Build | High | KM-GEN-FR006, KM-AUTH-FR004, FR005 | §8.2 | Knowledge Mgmt | Authoring Module | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0152 | WS-08: Knowledge Management | 8.1.7 | Build graphics/pictures embedding in KB articles | Build | Low | KM-AUTH-FR001 | §8.2 | Knowledge Mgmt | Rich Editor | Frontend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0153 | WS-08: Knowledge Management | 8.1.8 | Build spell check functionality | Build | Low | KM-AUTH-FR002 | §8.2 | Knowledge Mgmt | Spell Check | Frontend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0154 | WS-08: Knowledge Management | 8.1.9 | Build KB templates for manual document creation | Build | Medium | KM-AUTH-FR003 | §8.2 | Knowledge Mgmt | KB Templates | Business Analyst | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0155 | WS-08: Knowledge Management | 8.1.10 | Build Boolean-logic and natural language query support | Build | High | KM-SRCH-FR006, FR007 | §8.2 | Knowledge Mgmt | Advanced Search | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0156 | WS-08: Knowledge Management | 8.1.11 | Build customizable thesaurus (synonyms/acronyms) | Build | Medium | KM-SRCH-FR003 | §8.2 | Knowledge Mgmt | Thesaurus Config | Content Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0157 | WS-08: Knowledge Management | 8.1.12 | Build cross-source search with unified view | Build | Medium | KM-GEN-FR010 | §8.2 | Knowledge Mgmt | Federated Search | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0158 | WS-08: Knowledge Management | 8.1.13 | Build self-service KB access via intranet/internet | Build | High | KM-GEN-FR011 | §8.2 | Knowledge Mgmt | Self-Service KB | Frontend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0159 | WS-08: Knowledge Management | 8.1.14 | Configure KB access control by user category | Build | High | GEN-FR015 | §8.2 | Knowledge Mgmt | KB RBAC | Security Lead | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0160 | WS-08: Knowledge Management | 8.1.15 | Build modification history tracking | Build | Medium | KM-AUTH-FR006 | §8.2 | Knowledge Mgmt | Audit Trail | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0161 | WS-08: Knowledge Management | 8.1.16 | KM module testing | Testing | High | All KM | §6.7 | Knowledge Mgmt | Test Report | QA Engineer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0162 | WS-09: SLA & Reporting | 9.1.1 | Configure service description and catalog with quality levels | Build | High | SLM-FR001 | §8.2 | SLA Mgmt | Service Definitions | SLA Manager | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0163 | WS-09: SLA & Reporting | 9.1.2 | Build service-to-business-function association | Build | Medium | SLM-FR002 | §8.2 | SLA Mgmt | Service Mapping | Business Analyst | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0164 | WS-09: SLA & Reporting | 9.1.3 | Configure SLA targets (quantity/quality levels) | Build | High | SLM-FR003 | §8.2 | SLA Mgmt | SLA Target Config | SLA Manager | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0165 | WS-09: SLA & Reporting | 9.1.4 | Build SLA review cycle and lifespan management | Build | Medium | SLM-FR004 | §8.2 | SLA Mgmt | SLA Lifecycle Mgmt | SLA Manager | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0166 | WS-09: SLA & Reporting | 9.1.5 | Build Underpinning Contract and OLA management | Build | High | SLM-FR005 | §8.2 | SLA Mgmt | UC/OLA Module | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0167 | WS-09: SLA & Reporting | 9.1.6 | Build SLA-UC-OLA consistency verification engine | Build | High | SLM-FR006 | §8.2 | SLA Mgmt | Consistency Checker | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0168 | WS-09: SLA & Reporting | 9.1.7 | Build automated threshold monitoring against SLAs | Build | Critical | SLM-FR007 | §8.2 | SLA Mgmt | Threshold Monitor | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0169 | WS-09: SLA & Reporting | 9.1.8 | Build SLA reporting (achievements, breaches, exceptions) | Build | High | SLM-FR008 | §8.2 | SLA Mgmt | SLA Reports | BI Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0170 | WS-09: SLA & Reporting | 9.1.9 | Build multi-source data capture for end-to-end service view | Build | Medium | SLM-FR009 | §8.2 | SLA Mgmt | Data Aggregator | BI Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0171 | WS-09: SLA & Reporting | 9.1.10 | Build real-time graphical service summaries with threshold alerts | Build | High | SLM-FR010 | §8.2 | SLA Mgmt | Service Dashboard | Frontend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0172 | WS-09: SLA & Reporting | 9.1.11 | Build audience-specific SLM report customization | Build | Medium | SLM-FR011 | §8.2 | SLA Mgmt | Report Customizer | BI Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0173 | WS-09: SLA & Reporting | 9.1.12 | Build reporting engine (predefined + custom, tabular/graphical) | Build | High | RPT-UR001 to UR006 | §8.3 | Reporting | Report Engine | BI Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0174 | WS-09: SLA & Reporting | 9.1.13 | Build Query Builder for ad-hoc reports | Build | High | RPT-UR007 | §8.3 | Reporting | Query Builder | BI Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0175 | WS-09: SLA & Reporting | 9.1.14 | Build MTTR report generation | Build | High | RPT-UR008 | §8.3 | Reporting | MTTR Report | BI Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0176 | WS-09: SLA & Reporting | 9.1.15 | Build scheduled report email distribution | Build | Medium | RPT-UR003 | §8.3 | Reporting | Report Scheduler | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0177 | WS-09: SLA & Reporting | 9.1.16 | SLA and Reporting module testing | Testing | High | All SLM/RPT | §6.7 | SLA/Reporting | Test Report | QA Engineer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0178 | WS-10: Security & Compliance | 10.1.1 | Configure RBAC framework (roles, permissions, user groups) | Build | Critical | SEC-SR002, SR006, SR015 | §9.1 | Security | RBAC Framework | Security Architect | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0179 | WS-10: Security & Compliance | 10.1.2 | Configure user access admin (create, modify, deactivate) | Build | High | SEC-SR003, SR008, SR012 | §9.1 | Security | User Admin Module | Security Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0180 | WS-10: Security & Compliance | 10.1.3 | Configure admin GUI access restriction | Build | High | SEC-SR004 | §9.1 | Security | Admin Access Control | Security Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0181 | WS-10: Security & Compliance | 10.1.4 | Build login validation and session timeout | Build | High | SEC-SR005, SR010, SR013 | §9.1 | Security | Auth Module | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0182 | WS-10: Security & Compliance | 10.1.5 | Configure password policy enforcement per Bank standards | Build | High | SEC-SR009 | §9.1 | Security | Password Policy | Security Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0183 | WS-10: Security & Compliance | 10.1.6 | Build self-service password change | Build | Medium | SEC-SR011 | §9.1 | Security | Self-Service Auth | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0184 | WS-10: Security & Compliance | 10.1.7 | Configure TLS/SSL encryption for all communications | Build | Critical | SEC-SR007, SR016, SR020 | §9.1 | Security | Transport Security | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0185 | WS-10: Security & Compliance | 10.1.8 | Configure data-at-rest encryption | Build | Critical | SEC-SR026 | §9.1 | Security | Storage Encryption | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0186 | WS-10: Security & Compliance | 10.1.9 | Build comprehensive audit logging in syslog format | Build | Critical | SEC-SR014, SR017 | §9.1 | Security | Audit Logger | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0187 | WS-10: Security & Compliance | 10.1.10 | Integrate with Bank IAM solution | Build | Critical | SEC-SR018 | §9.1 | Security | IAM Integration | Integration Dev | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0188 | WS-10: Security & Compliance | 10.1.11 | Integrate with AD/LDAP/SAML as authentication source | Build | Critical | SEC-SR019 | §9.1 | Security | Directory Integration | Integration Dev | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0189 | WS-10: Security & Compliance | 10.1.12 | Integrate audit logs with SIEM solution | Build | High | SEC-SR017 | §9.1 | Security | SIEM Integration | Integration Dev | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0190 | WS-10: Security & Compliance | 10.1.13 | Configure MFA enforcement | Build | High | SEC-SR024 | §9.1 | Security | MFA Module | Security Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0191 | WS-10: Security & Compliance | 10.1.14 | Implement NDPR and GDPR privacy compliance controls | Build | High | SEC-SR025 | §9.1 | Security | Privacy Controls | Privacy Officer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0192 | WS-10: Security & Compliance | 10.1.15 | Configure data classification scheme alignment | Build | High | SEC-SR021 | §9.1 | Security | Data Classification | Security Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0193 | WS-10: Security & Compliance | 10.1.16 | Conduct code security testing and vulnerability remediation | Build | Critical | SEC-SR027 | §9.1 | Security | SAST/DAST Reports | Security Tester | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0194 | WS-10: Security & Compliance | 10.1.17 | Configure secure patching and update mechanism | Build | Medium | SEC-SR023 | §9.1 | Security | Patch Mgmt Config | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0195 | WS-10: Security & Compliance | 10.1.18 | Build data source validation controls | Build | Medium | SEC-SR001 | §9.1 | Security | Input Validation | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0196 | WS-10: Security & Compliance | 10.1.19 | Build audit trail report with full detail (record ID, timestamp, user, table, action, before/after values) | Build | High | ICR001, ICR002 | §9.7 | Security | Audit Trail Report | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0197 | WS-10: Security & Compliance | 10.1.20 | Security penetration testing | Testing | Critical | All SEC | §6.7 | Security | Pen Test Report | Security Tester | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0198 | WS-10: Security & Compliance | 10.1.21 | Security architecture review and sign-off (ISMD) | Governance | High | All SEC | §9.1 | Security | Security Sign-off | Security Architect | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0199 | WS-10: Security & Compliance | 10.1.22 | Conduct vulnerability assessment | Testing | High | SEC-SR027 | §9.1 | Security | VA Report | Security Tester | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0200 | WS-10: Security & Compliance | 10.1.23 | Configure access control effectiveness reporting | Build | Medium | SEC-SR014 | §9.1 | Security | Access Reports | Security Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0201 | WS-10: Security & Compliance | 10.1.24 | DR/BC security controls validation | Testing | High | SEC-SR022 | §9.4 | Security | DR Security Tests | Security Tester | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0202 | WS-10: Security & Compliance | 10.1.25 | Privacy impact assessment | Governance | High | SEC-SR025 | §9.1 | Security | PIA Report | Privacy Officer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0203 | WS-10: Security & Compliance | 10.1.26 | ISO 27001 compliance validation | Governance | Critical | All SEC | §9.1 | Security | ISO Compliance Report | Security Architect | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0204 | WS-10: Security & Compliance | 10.1.27 | Security module testing | Testing | High | All SEC | §6.7 | Security | Test Report | QA Engineer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0205 | WS-11: Integration | 11.1.1 | Build Active Directory integration (user sync, authentication) | Build | Critical | GEN-FR017, SEC-SR019 | §9.9 | Integration | AD Integration | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0206 | WS-11: Integration | 11.1.2 | Build Microsoft Azure SSO integration | Build | Critical | Scope §5.0 | §5.0 | Integration | Azure SSO | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0207 | WS-11: Integration | 11.1.3 | Build Microsoft Teams integration (notifications, chatbot) | Build | High | Scope §5.0 | §5.0 | Integration | Teams Integration | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0208 | WS-11: Integration | 11.1.4 | Build MEGA EA tool integration via XSD/XML | Build | High | IR001 | §9.9 | Integration | EA Integration | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0209 | WS-11: Integration | 11.1.5 | Build SCCM integration for license utilization management | Build | High | IR002 | §9.9 | Integration | SCCM Integration | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0210 | WS-11: Integration | 11.1.6 | Build Oracle ERP integration | Build | Medium | GEN-FR017 | §8.2 | Integration | ERP Integration | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0211 | WS-11: Integration | 11.1.7 | Build mobile device support and responsive design | Build | High | Scope §5.0 | §5.0 | Integration | Mobile Support | Frontend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0212 | WS-11: Integration | 11.1.8 | Build email-to-ticket integration (ithelpdesk@cbn.gov.ng) | Build | High | GEN-FR011 | §8.2 | Integration | Email Integration | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0213 | WS-11: Integration | 11.1.9 | Build REST/SOAP API layer for third-party integrations | Build | High | GEN-FR017 | §8.2 | Integration | API Gateway | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0214 | WS-11: Integration | 11.1.10 | Configure chatting capability on mobile devices | Build | Medium | BR-005 | §3.0 | Integration | Chat Module | Frontend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0215 | WS-11: Integration | 11.1.11 | Build CMDB-to-ITSM cross-module data integration | Build | High | UI001, MR001 | §9.8 | Integration | Module Integration | Backend Developer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0216 | WS-11: Integration | 11.1.12 | Build ticket system interface with infrastructure systems | Build | High | UI002 | §9.8 | Integration | Infra Integration | Integration Dev | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0217 | WS-11: Integration | 11.1.13 | Integration testing (all integration points) | Testing | Critical | All IR/UI | §6.7 | Integration | Integration Test Report | QA Lead | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0218 | WS-11: Integration | 11.1.14 | Build encrypted communication for all web services | Build | High | GEN-FR016 | §8.2 | Integration | WS Security | Security Lead | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0219 | WS-11: Integration | 11.1.15 | API documentation and developer portal | Documentation | Medium | GEN-FR017 | §8.2 | Integration | API Documentation | Technical Writer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0220 | WS-11: Integration | 11.1.16 | Integration stress/performance testing | Testing | High | All integrations | §6.7 | Integration | Stress Test Report | QA Engineer | TBD | Phase 2 | 2 |  |  |  | Not Started | 0%
TSK-0221 | WS-12: UI/UX & Platform | 12.1.1 | Configure self-guided navigation | Build | High | GEN-FR001, OR001-FR001 | §8.2 | Platform | Navigation Config | UX Designer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0222 | WS-12: UI/UX & Platform | 12.1.2 | Build role-based GUI separation | Build | High | GEN-FR013 | §8.2 | Platform | Role-Based UI | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0223 | WS-12: UI/UX & Platform | 12.1.3 | Build multi-tenant Contact Centre data isolation | Build | High | GEN-FR009 | §8.2 | Platform | Multi-Tenant Config | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0224 | WS-12: UI/UX & Platform | 12.1.4 | Configure input controls (dropdowns, calendars, radio buttons) | Build | Medium | OR003 | §9.2 | Platform | Input Controls | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0225 | WS-12: UI/UX & Platform | 12.1.5 | Build error handling with interpretable messages | Build | Medium | OR005, OR006 | §9.2 | Platform | Error Handling | Backend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0226 | WS-12: UI/UX & Platform | 12.1.6 | Build context-sensitive help and documentation | Build | Medium | OR011 | §9.2 | Platform | Help System | Technical Writer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0227 | WS-12: UI/UX & Platform | 12.1.7 | Configure consistent, readable page layouts | Build | Medium | OR007 | §9.2 | Platform | Layout Templates | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0228 | WS-12: UI/UX & Platform | 12.1.8 | Build user feedback mechanism on closed issues | Build | Low | GEN-FR010 | §8.2 | Platform | Feedback Module | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0229 | WS-12: UI/UX & Platform | 12.1.9 | Optimize page load performance | Build | High | OR008 | §9.2 | Platform | Performance Optimization | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0230 | WS-12: UI/UX & Platform | 12.1.10 | Configure login experience (seamless, SSO-ready) | Build | High | OR009 | §9.2 | Platform | Login UI | Frontend Developer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0231 | WS-12: UI/UX & Platform | 12.1.11 | Usability testing with representative users | Testing | High | All UI/UX | §6.7 | Platform | Usability Test Report | UX Designer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0232 | WS-12: UI/UX & Platform | 12.1.12 | Accessibility compliance review | Testing | Low | OR010 | §9.2 | Platform | Accessibility Report | UX Designer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0233 | WS-13: Infrastructure & HA/DR | 13.1.1 | Provision virtualized infrastructure (VMware/Hyper-V) | Infrastructure | Critical | OR012 | §9.2 | Infrastructure | VM Provisioning | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0234 | WS-13: Infrastructure & HA/DR | 13.1.2 | Configure development environment | Infrastructure | High | GEN-FR007 | §8.2 | Infrastructure | Dev Environment | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0235 | WS-13: Infrastructure & HA/DR | 13.1.3 | Configure testing environment | Infrastructure | High | GEN-FR007 | §8.2 | Infrastructure | Test Environment | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0236 | WS-13: Infrastructure & HA/DR | 13.1.4 | Configure production environment | Infrastructure | Critical | GEN-FR007 | §8.2 | Infrastructure | Prod Environment | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0237 | WS-13: Infrastructure & HA/DR | 13.1.5 | Configure High Availability architecture (99.9%) | Infrastructure | Critical | BC001, GEN-FR006, GEN-FR014 | §9.4 | Infrastructure | HA Configuration | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0238 | WS-13: Infrastructure & HA/DR | 13.1.6 | Configure failover procedures and testing | Infrastructure | Critical | GEN-FR014 | §8.2 | Infrastructure | Failover Procedures | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0239 | WS-13: Infrastructure & HA/DR | 13.1.7 | Configure backup strategy per Bank policy | Infrastructure | High | BC002 | §9.4 | Infrastructure | Backup Config | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0240 | WS-13: Infrastructure & HA/DR | 13.1.8 | Configure Disaster Recovery for CMDB (99.99%) | Infrastructure | Critical | DR001 | §9.11 | Infrastructure | DR Configuration | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0241 | WS-13: Infrastructure & HA/DR | 13.1.9 | Configure network protocols per Bank standards | Infrastructure | High | MR004 | §9.6 | Infrastructure | Network Config | Network Engineer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0242 | WS-13: Infrastructure & HA/DR | 13.1.10 | Configure web browser compatibility (IE, Firefox, etc.) | Infrastructure | Medium | MR005 | §9.6 | Infrastructure | Browser Testing | QA Engineer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0243 | WS-13: Infrastructure & HA/DR | 13.1.11 | Configure database integration (common access method) | Infrastructure | High | MR002 | §9.6 | Infrastructure | DB Config | DB Admin | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0244 | WS-13: Infrastructure & HA/DR | 13.1.12 | DR failover testing | Testing | Critical | DR001, BC001 | §9.11 | Infrastructure | DR Test Report | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0245 | WS-13: Infrastructure & HA/DR | 13.1.13 | Performance/load testing (concurrent users) | Testing | High | PR001-PR009 | §9.5 | Infrastructure | Load Test Report | QA Engineer | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0246 | WS-13: Infrastructure & HA/DR | 13.1.14 | Availability target validation (99.999%) | Testing | High | AR001 | §9.10 | Infrastructure | Availability Report | Infrastructure Lead | TBD | Phase 1 | 2 |  |  |  | Not Started | 0%
TSK-0247 | WS-14: Testing & QA | 14.1.1 | Develop master test plan | Planning | Critical | All | §6.6 | Testing | Master Test Plan | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0248 | WS-14: Testing & QA | 14.1.2 | Develop test cases for all 234 requirements | Planning | Critical | All RTM | §6.7 | Testing | Test Case Library | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0249 | WS-14: Testing & QA | 14.1.3 | Configure test environment and test data | Build | High | GEN-FR007 | §6.7 | Testing | Test Environment | QA Engineer | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0250 | WS-14: Testing & QA | 14.1.4 | Execute system testing (all modules) | Testing | Critical | All | §6.7 | Testing | System Test Report | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0251 | WS-14: Testing & QA | 14.1.5 | Execute unit testing | Testing | High | All | §6.7 | Testing | Unit Test Report | Developers | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0252 | WS-14: Testing & QA | 14.1.6 | Execute integration testing (cross-module) | Testing | Critical | All | §6.7 | Testing | Integration Test Report | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0253 | WS-14: Testing & QA | 14.1.7 | Execute stress/performance testing | Testing | High | PR001-PR009 | §6.7 | Testing | Stress Test Report | QA Engineer | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0254 | WS-14: Testing & QA | 14.1.8 | Execute security testing (SAST, DAST, penetration) | Testing | Critical | All SEC | §6.7 | Testing | Security Test Report | Security Tester | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0255 | WS-14: Testing & QA | 14.1.9 | Execute data conversion testing | Testing | High | CMDB migration | §6.7 | Testing | Data Test Report | QA Engineer | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0256 | WS-14: Testing & QA | 14.1.10 | Prepare UAT test scripts and schedule | Planning | High | All | §6.7 | Testing | UAT Scripts | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0257 | WS-14: Testing & QA | 14.1.11 | Request UAT nominees from user groups | Coordination | High | Process §6.7 step 7.3 | §6.7 | Testing | Nominee List | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0258 | WS-14: Testing & QA | 14.1.12 | Execute User Acceptance Testing | Testing | Critical | All | §6.7 | Testing | UAT Sign-off | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0259 | WS-14: Testing & QA | 14.1.13 | Defect management and resolution tracking | Testing | High | All | §6.7 | Testing | Defect Log | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0260 | WS-14: Testing & QA | 14.1.14 | Regression testing after defect fixes | Testing | High | All | §6.7 | Testing | Regression Report | QA Engineer | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0261 | WS-14: Testing & QA | 14.1.15 | Test closure report and sign-off | Governance | High | All | §6.7 | Testing | Test Closure Report | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0262 | WS-14: Testing & QA | 14.1.16 | Prepare implementation certificate | Governance | Critical | Process §6.5 | §6.5 | Testing | Implementation Certificate | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0263 | WS-14: Testing & QA | 14.1.17 | Non-functional testing (usability, accessibility, browser compat) | Testing | Medium | OR001-OR012 | §9.2 | Testing | NFR Test Report | QA Engineer | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0264 | WS-14: Testing & QA | 14.1.18 | End-to-end process testing (all 8 ITIL workflows) | Testing | Critical | All processes | §6.0 | Testing | E2E Test Report | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0265 | WS-14: Testing & QA | 14.1.19 | Acceptance criteria validation against BRD | Testing | High | All | §8.0 | Testing | Validation Report | Business Analyst | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0266 | WS-14: Testing & QA | 14.1.20 | Operational readiness testing | Testing | High | All | §6.5 | Testing | ORT Report | QA Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0267 | WS-14: Testing & QA | 14.1.21 | Test automation setup for regression suite | Build | Medium | All | §6.7 | Testing | Automation Framework | QA Engineer | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0268 | WS-14: Testing & QA | 14.1.22 | Test data management and cleanup | Operations | Medium | All | §6.7 | Testing | Test Data Mgmt | QA Engineer | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0269 | WS-15: Data Migration | 15.1.1 | Audit existing CI data in Excel spreadsheets | Analysis | Critical | CMDB-FR009 | §6.9 | Migration | Data Audit Report | Migration Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0270 | WS-15: Data Migration | 15.1.2 | Define data mapping rules (Excel columns → CMDB schema) | Design | Critical | CMDB-FR009 | §6.9 | Migration | Data Mapping Doc | Migration Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0271 | WS-15: Data Migration | 15.1.3 | Build data cleansing scripts and rules | Build | High | CMDB-FR009 | §6.9 | Migration | Cleansing Scripts | Migration Dev | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0272 | WS-15: Data Migration | 15.1.4 | Build ETL pipeline for CI data migration | Build | High | CMDB-FR009 | §6.9 | Migration | ETL Pipeline | Migration Dev | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0273 | WS-15: Data Migration | 15.1.5 | Execute trial migration in test environment | Testing | Critical | CMDB-FR009 | §6.9 | Migration | Trial Migration Report | Migration Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0274 | WS-15: Data Migration | 15.1.6 | Validate migrated data against source (reconciliation) | Testing | Critical | CMDB-FR017 | §6.9 | Migration | Reconciliation Report | Migration Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0275 | WS-15: Data Migration | 15.1.7 | Physical CI audit and verification | Testing | High | CMDB-FR023 | §6.9 | Migration | Physical Audit Report | Asset Team | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0276 | WS-15: Data Migration | 15.1.8 | Execute production data migration | Operations | Critical | CMDB-FR009 | §6.9 | Migration | Migration Completion | Migration Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0277 | WS-15: Data Migration | 15.1.9 | Post-migration validation and sign-off | Testing | Critical | CMDB-FR009 | §6.9 | Migration | Migration Sign-off | Migration Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0278 | WS-15: Data Migration | 15.1.10 | Build cutover plan and rollback procedure | Planning | Critical | Process §6.5 | §6.5 | Migration | Cutover Plan | Migration Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0279 | WS-15: Data Migration | 15.1.11 | ServiceNow decommission plan | Planning | High | All | §2.0 | Migration | Decommission Plan | Infrastructure Lead | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0280 | WS-15: Data Migration | 15.1.12 | Legacy data archival strategy | Planning | Medium | All | §2.0 | Migration | Archival Plan | DB Admin | TBD | Phase 3 | 2 |  |  |  | Not Started | 0%
TSK-0281 | WS-16: Training & Change Mgmt | 16.1.1 | Develop training needs assessment | Planning | High | GEN-FR002 | §8.2 | Training | TNA Report | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0282 | WS-16: Training & Change Mgmt | 16.1.2 | Develop admin/configuration training materials | Build | High | All admin tasks | §8.2 | Training | Admin Training Pack | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0283 | WS-16: Training & Change Mgmt | 16.1.3 | Develop service desk analyst training materials | Build | High | INC/REQ/PM modules | §8.2 | Training | SD Training Pack | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0284 | WS-16: Training & Change Mgmt | 16.1.4 | Develop end-user self-service training materials | Build | Medium | REQ-FR004, KM-GEN-FR011 | §8.2 | Training | User Training Pack | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0285 | WS-16: Training & Change Mgmt | 16.1.5 | Develop CMDB administrator training materials | Build | High | CMDB-FR001 to FR032 | §8.2 | Training | CMDB Training Pack | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0286 | WS-16: Training & Change Mgmt | 16.1.6 | Develop change/release manager training materials | Build | High | CHG-FR001 to FR012 | §8.2 | Training | Change Mgmt Training | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0287 | WS-16: Training & Change Mgmt | 16.1.7 | Conduct train-the-trainer sessions | Training | High | All | §8.2 | Training | TTT Session Records | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0288 | WS-16: Training & Change Mgmt | 16.1.8 | Conduct ITD staff training (all divisions) | Training | Critical | All | §4.0 | Training | Training Records | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0289 | WS-16: Training & Change Mgmt | 16.1.9 | Conduct business department training (DFD, OFISD, etc.) | Training | High | REQ/INC modules | §4.0 | Training | Dept Training Records | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0290 | WS-16: Training & Change Mgmt | 16.1.10 | Develop organizational change management plan | Change Mgmt | Critical | All | §4.0 | Change Mgmt | OCM Plan | Change Manager | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0291 | WS-16: Training & Change Mgmt | 16.1.11 | Stakeholder readiness assessment | Change Mgmt | High | All | §4.0 | Change Mgmt | Readiness Report | Change Manager | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0292 | WS-16: Training & Change Mgmt | 16.1.12 | Develop user adoption strategy and metrics | Change Mgmt | High | All | §4.0 | Change Mgmt | Adoption Strategy | Change Manager | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0293 | WS-16: Training & Change Mgmt | 16.1.13 | Develop support documentation (user guides, FAQs, quick refs) | Documentation | Medium | All | §8.2 | Training | User Documentation | Technical Writer | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0294 | WS-16: Training & Change Mgmt | 16.1.14 | Conduct knowledge transfer sessions from vendor | Training | High | All | — | Training | KT Session Records | Training Lead | TBD | Phase 4 | 2 |  |  |  | Not Started | 0%
TSK-0295 | WS-17: Go-Live & Post-Implementation | 17.1.1 | Finalize go-live checklist and readiness assessment | Planning | Critical | All | §6.5 | Go-Live | Go-Live Checklist | Delivery Manager | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0296 | WS-17: Go-Live & Post-Implementation | 17.1.2 | Execute go-live deployment | Operations | Critical | All | §6.5 | Go-Live | Deployment Report | Delivery Manager | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0297 | WS-17: Go-Live & Post-Implementation | 17.1.3 | Establish hypercare support team and escalation path | Operations | Critical | All | — | Go-Live | Hypercare Plan | Service Desk Lead | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0298 | WS-17: Go-Live & Post-Implementation | 17.1.4 | Monitor system performance post-go-live (first 30 days) | Monitoring | High | PR001-PR009, AR001 | §9.5 | Go-Live | Performance Report | Infrastructure Lead | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0299 | WS-17: Go-Live & Post-Implementation | 17.1.5 | Conduct post-implementation review (PIR) | Governance | High | CHG process §6.4 step 6.4 | §6.4 | Go-Live | PIR Report | Project Manager | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0300 | WS-17: Go-Live & Post-Implementation | 17.1.6 | Transition to BAU support model | Operations | High | All | — | Go-Live | BAU Transition Plan | Service Desk Lead | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0301 | WS-17: Go-Live & Post-Implementation | 17.1.7 | Handover documentation to operations team | Documentation | High | All | — | Go-Live | Handover Pack | Delivery Manager | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0302 | WS-17: Go-Live & Post-Implementation | 17.1.8 | Close project and produce lessons learned | Governance | Medium | All | — | Go-Live | Project Closure Report | Project Manager | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0303 | WS-17: Go-Live & Post-Implementation | 17.1.9 | Vendor SLA monitoring setup for ongoing support | Operations | High | All | §8.2 | Go-Live | Vendor SLA Dashboard | SLA Manager | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
TSK-0304 | WS-17: Go-Live & Post-Implementation | 17.1.10 | Decommission ServiceNow | Operations | High | All | §2.0 | Go-Live | Decommission Report | Infrastructure Lead | TBD | Phase 5 | 2 |  |  |  | Not Started | 0%
© Information Technology Department, Central Bank of Nigeria ¦ Classified as Confidential